## Projects
Release | Project ID | PMT | Project Name | INTFC_VRSN_CNTER_GRP.INTERFACE_PROGRAM (Mobility, VoIP, L3, DTV, uVerse) | INTFC_VRSN_CNTER_GRP.INTERFACE_PROGRAM_SUB (vendor & NE) | INTFC_VRSN_CNTER_GRP_FILE_LOC.DOMAIN (D1, D1.5, D2.0) | Impact | iPOR Lead Developer | Developers | IT / Sprint Schedule | LPM | PM | Scrum Master | SE | Notes | Readiness Status | CR # Used for Deployment | Operational Readiness Date (Ops needs to include new or existing feeds into log reports)
1508 | 284335 | 445089 |  | DCAE |  |  |  | Fani
1507 | 277170 | 435176 | Trinity - Hosted VoIP Platform Consolidation | Trinity |  |  | Code | Fani
1510 | 277170M | 440094 | Trinity Hosted Voice Consolidation - October 2015 | Trinity |  |  | Code | Fani | Srinivas Wes | IT 19: 6/22/2015-7/17/2015 IT 19: 9/14/2015-10/2/2015 (Dev & Test) IT 20: 9/14/2015-10/2/2015 IT 20: 9/14/2015-10/2/2015 (Dev & Test) IT 21: 10/5/2015-10/30/2015 IT 21: 10/5/2015-10/30/2015 (Dev & Test) IT 21: 11/2/2015-11/13/2015 (IST) IT 21: 11/9/2015-12/4/2015 (UAT & ETE) |  | Jane Eisenmann (je3134) |  | Minsky Luo (ml106g)
1512 | 277170O | 440917 | Trinity Hosted Voice Consolidation - December 2015 | Trinity |  |  | Code | Eric / Fani | Srinivas Wes | IT 22: 9/14/2015-10/2/2015 IT 22: 9/14/2015-10/2/2015 (Dev & Test) IT 23: 10/5/2015-10/30/2015 IT 23: 10/5/2015-10/30/2015 (Dev & Test) IT 23: 11/2/2015-11/13/2015 (IST) IT 23: 11/9/2015-12/4/2015 (UAT & ETE) |  | Jane Eisenmann (je3134) | ?? | Minsky Luo (ml106g) | New DMD work is coming in. Tim/Jane will schedule a meeting for Wednesday, 11/4.
1602 | 277170P | 442399 | Trinity Hosted Voice Consolidation - February 2016 | Trinity |  |  | Code | Eric | ?? | IT24: 11/2/2016-11/27/2016 IT25: 11/30/2016-12/25/2016 IT26: 12/28/2016-1/22/2016 IT27: 1/25/2016-2/12/2016 IT28: 2/15/2016-3/4/2016 |  | Jane Eisenmann (je3134) | ?? | Minsky Luo (ml106g) | VETL will be doing OHDR work in this project. Minskey will go over the US for this work on Tuesday, 11/3. Need to include Ravi into this meeting since there are old and new OHDR and Ravi was part of old OHDR.
1602 | 278772c | 446644 | IR94 Integrity - Media 2 KPIs | Trinity |  |  | No impact | Eric | [5 empty] | Brijvihari Pathak
1604 | 289045 / CR141957 | 454323 | Hardware Ingest ECOMP 162 | Trinity |  |  | Code | Eric & Johan | Wes |  |  | Jane Eisenmann (je3134) | ?? | Minsky Luo (ml106g) | 3/29: Eric, Johan, Wes & Tony attended the meeting to understand what is needed in this urgent request.
1607 | 288304 | 454886 | Trinity over AVPN Private Network | Trinity |  |  | Code | Ravi | Ravi - ry3304 | ?? |  | Jane Eisenmann (je3134) | ?? | Minsky Luo (ml106g) | 3/22: Srinivas attend the last 30 mins out of 1.5 hours of the US review session today. Minsky will schedule a 2nd call with VETL for tomorrow to review the Uss. 6/28: No data model changes, only metadata changes to add new entries to file_loc table.
1610 | 291098 | ?? | Trinity - Hosted VoIP platform - R2 | Trinity |  |  | TSO | Eric | Srinivas | IT1: 06/27/2016 to 07/22/2016 IT2: 07/25/2016 to 08/19/2016 IT3: 08/22/2016 to 09/02/2016 |  | Jane Eisenmann (je3134) | Jane Eisenmann (je3134) | Minsky Luo (ml106g) | 6/7: Srinivas confirmed that this column is already being increased in 1607 so this 1 US for VETL/Vertica in this project is TSO. Minsky marked the US as TSO. 6/4: Eric & Srinivas attended a US review session that has just 1 US for VETL/Vertica to do the below: Increase DV0_DCAECOMMON_DB.CEILHOSTCOMPUTESTATS.RESOURCEID columns to VARCHAR2(200) | 9/28 Eric: TSO, nothing to deploy
1702 | 283081 | 458801 | (VIP)Trinity-Hosted VoIP Pltfrm Consdtn | Trinity |  |  | Code | Eric | Yeab (DMaaP DR) Jerome (DMaaP MR) Cynthia (DM, MD) Alan (DM, MD) Srinivas (DM, MD) Wes (DM, MD) Sachin (DM,MD) Vinayak (DM, MD) | IT1: 9/12/2016 to 10/9/2016 IT2: 10/10/2016 to 11/6/2016 IT3: 11/7/2016 to 12/4/2016 |  | Jane Eisenmann (je3134) | Jane Eisenmann (je3134) | Minsky Luo (ml106g) | 9/16: Minsky held his first US review session 9/15: Didi held his first US review session
1702 | 291098A | 458936 | Trinity - Hosted VoIP platform - R2 - Scope Move | Trinity |  |  | Code | Eric | Yeab (DMaaP DR) Jerome (DMaaP MR) Cynthia (DM, MD) Alan (DM, MD) Srinivas (DM, MD) Wes (DM, MD) | IT1: 9/12/2016 to 10/9/2016 IT2: 10/10/2016 to 11/6/2016 IT3: 11/7/2016 to 12/4/2016 |  | Jane Eisenmann (je3134) | Jane Eisenmann (je3134) | Minsky Luo (ml106g) | 9/16: Minsky held his first US review session 9/15: Didi held his first US review session
1807 1707 | 287479 | 458774 | IP Flex Enhanced Features Server Scaling R2 | vFlex |  |  | Code | Eric | Manish (DMD, DM, MD) Senthil (DM, MD) Alan (KPI, MD) | New HALO schedule to use IT0 - 01/16/2017 – 02/10/2017 IT1 – 02/13/2017 – 03/10/2017 IT2 – 03/13/2017 – 04/07/2017 IT3 – 04/10/2017 – 05/05/2017 This IT schedule is NOT being used anymore IT1 01/18/2017 – 02/07/2017 IT2 02/08/2017 – 02/28/2017 IT3 03/01/2017 – 03/21/2017 IT4 03/22/2017 – 04/11/2017 IT5 04/12/2017 – 05/02/2017 IT6 05/03/2017 – 05/23/2017 |  | Emily Montgomery (es9137) | Emily Montgomery (es9137) | Minsky Luo (ml106g) | 1/5: Eric & Srinivas attended the 1st US review session held by Minsky
1510 | 284249a | 447762 | ALU vUSP Network OSS - 1510 | vUSP |  |  | Code | Fani |  |  |  | Jane Eisenmann (je3134) |  |  | 9/28: Srini loaded new data on 9/26. Everything is now loading automatically. As of today, no emails/issues from ST.
1602 | 284249 | 446814 | ALU vUSP Network OSS for IMS 133140 | vUSP |  |  | Code | Johan | TechM | IT 1: 10/5/2015-10/23/2015 IT 2: 10/26/2015-11/13/2015 IT 3: 11/16/2015-12/4/2015 (Dev) IT 4: 12/7/2015-12/25/2015 (Dev) IT 5: 12/28/2015-1/15/2016 IT 6: 1/18/2016-2/5-2016 IT 7: 2/9/2016-2/26/2016 IT 8: 2/29/2016-3/18/2016 TBD: (IST & ETE) TBD: (Defect only << Final ETE) |  | Jane Eisenmann (je3134) Syed Hyder (sh7615) | Nabil Esphahani (ne6472) | Deepa Saxena (ds521a) (PM) Ed Berberich (eb1847) (PM & CTI) Didi Xie (dx080q) (CDR) Ming-Ming Yu (my2263) (CDR)
1603 | 284249 | 446814 | ALU vUSP Network OSS for IMS 133140 | vUSP |  |  | Code | Johan | TechM | IT 1: 10/5/2015-10/23/2015 IT 2: 10/26/2015-11/13/2015 IT 3: 11/16/2015-12/4/2015 (Dev) IT 4: 12/7/2015-12/25/2015 (Dev) IT 5: 12/28/2015-1/15/2016 IT 6: 1/18/2016-2/5-2016 IT 7: 2/9/2016-2/26/2016 IT 8: 2/29/2016-3/18/2016 TBD: (IST & ETE) TBD: (Defect only << Final ETE) |  | Jane Eisenmann (je3134) Syed Hyder (sh7615) | Nabil Esphahani (ne6472) | Deepa Saxena (ds521a) (PM) Ed Berberich (eb1847) (PM & CTI) Didi Xie (dx080q) (CDR) Ming-Ming Yu (my2263) (CDR)
1604 1603 | 285296 | 449769 | ALU vUSP D2.0 Advanced OSS (BNS) | vUSP |  |  | Code | Eric & Johan |  | IT 6: 1/18/2016-2/12/2016 (Dev) IT 7: 2/8/2016 – 2/26/2016 |  | Jane Eisenmann (je3134) | ?? | Ming-Ming Yu (my2263) | 1/18: Minsky had an official US grooming session. Johan, Srinivas, Wes and Eric attended. 1/11: Eric asked Jane on the PMOSS VOIP call today about this project. The project has not had any US review calls and is about to be kicked off but Jane does not have a date today on when that call will take place. 1/11: Eric spoke with Aleks Sisarica who is the PID owner in Prism. She does not have VETL/Vertica listed in her project at all but told me to speak with Jane Eisenmann since maybe PMOSS VOIP added VETL/Vertica into the project.
1605 | 285296A | 450290 | ALU vUSP D2 0 Advanced OSS (BNS) 1605 | vUSP |  |  | Code | Johan |  | IT8: 2/29/2016-3/18/2016 IT9: 3/21/2016-4/8/2016 IT10: 4/11/2016-4/29/2016 IT11: 5/2/2016-5/20/2016 IT12: 5/23/2016-6/10/2016 |  | Jane Eisenmann (je3134) | ?? | Ed Berberich (eb1847) Fil Deguzman (fd2432)
1607 | 285296B | 450289 | ALU vUSP D2 0 Advanced OSS (BNS) 1607 | vUSP |  |  |  | Johan | Yeab, Brett, Srinivas | IT8: 2/29/2016-3/18/2016 IT9: 3/21/2016-4/8/2016 IT10: 4/11/2016-4/29/2016 IT11: 5/2/2016-5/20/2016 IT12: 5/23/2016-6/10/2016 IT13: 6/13/2016-7/1/2016 |  | Jane Eisenmann (je3134) | ?? | Ed Berberich (eb1847) | 3/14: Eric has been invited for a US review session for 3/15.
1607 | 283554 | 450201 | (VIP) IP IC: Wholesale VoLTE/CVOIP 2 | vUSP |  |  | Code | Brij | DMD (CDR): Wes DMD (Inventory): Yeab DMD (PM): Yeab DM/MD (CDR): Wes, Binesh DM/MD (Inventory): Wes DM/MD (PM): Srinivas DM/MD (Ceilometer): Srinivas | SP 1: 4/20-5/10 SP 2: 5/11-5/31 |  | Jane Eisenmann (je3134) | Emily Montgomery (es9137) | Ming-Ming Yu (my2263), Didi Xie, Kin Wong | 4/21: Eric just found this project today assigned to Brij via Tony's project assignment spreadsheet. Brij will update all the required info on this project 3/22: Eric, Wes & Srinivas attended the xxxx meeting to go over the high level purpose of this project. Scope of work: VETL/Vertica to add new columns into existing USP CCF CDR tables, views and aggregation tables VETL/Vertica to create brand new custom views for Metaswitch vI-SBC data
1610 | 283554A | 455102 | (VIP) IP IC Wholesale VoLTE CVOIP 2 - Phase 2 | vUSP |  |  | Code | Eric | Jerome (xml parser) Wes (DM, MD) Alan (MD, KPI engine) Cynthia (KPI engine config) Cary (INSIGHT) | IT2 8/3/2016 - 8/23/2016 IT3 8/24/2016 - 9/13/2016 |  | Jane Eisenmann (je3134) | Emily Montgomery (es9137) | Ming-Ming Yu (my2263), Didi Xie, Kin Wong, Cary Hermann (ch1794 | 6/16: Brij/Didi had a project transition call with Eric today. Eric has a pretty good understanding of the work but there are still questions as listed in the desciption column (S). The US grooming session has not occurred yet so we don't know which iteration this work is actually do in 1610. 4/21: Eric just found this project today assigned to Brij via Tony's project assignment spreadsheet. Brij will update all the required info on this project 3/22: Eric, Wes & Srinivas attended the xxxx meeting to go over the high level purpose of this project. Scope of work: VETL/Vertica to add new columns into existing USP CCF CDR tables, views and aggregation tables VETL/Vertica to create brand new custom views for Metaswitch vI-SBC data | 9/26 Cynthia: KPI config completed in DEV & ST 9/28 Eric: Project is ready for deployment
1710 1707 1702 | 285296C | 457045 | 285296c - Features Support for vSBC-BGW VSBC-ISC VNF s | VoIP |  |  | Code | Eric | Gourav (DMaaP, DM, MD, KPI Engine) Alan (KPI Engine) Manish (DMD, DM, MD) | R08.1: 7/5/2017 - 7/25/2017 R08.2: 7/26/2017 - 8/15/2017 R08.3: 8/16/2017 - 9/5/2017 Old dates IT1 3/22/2017 - 4/11/2017 IT2 4/12/2017 - 5/2/2017 IT3 5/3/2017 - 5/23/2017 R07.4 (June 14 - July4) R008.01 (July 5 - July 25) R08.02 (July 26 - August 15) Old dates before project went on hold IT1 10/31/2016 - 11/25/2016 IT2 11/28/2106 - 12/23-2016 |  | Kris Hubble (wh4355) | Subrahmanyam Jonnavittula (sj896b) Kris Hubble (wh4355) | Ed Berberich (eb1847) | 11/3: This project got pushed back into 1710/1711 deployment. 10/18: This project will be deployed in 1802 and it will NOT deploy in 1710 dark. 7/10: Grooming session took place today and all work was assigned to Gourav 3/28: This project is now a 1710 project 11/21: Kris Hubble sent an email stating that this project is now moved to 1707. 11/16: Eric attended Ed's meeting with Hong Wang to discuss adding and deleting columns for two v3CDB existing tables. Eric provided 3 weeks (including overhead) of work to Kris Hubble. Kris will contact management and client to get green light to proceed. The US does NOT exist today. | 11/3: Ready to deploy 11/3: This project got pushed back into 1710/1711 deployment.
18?? 1802 1710 1707 1702 | 285296C | 471646 457045 | 285296c - Features Support for vSBC-BGW VSBC-ISC VNF s | VoIP |  |  | On hold | Eric | Kshama (DM, MD) |  |  | Kris Hubble (wh4355) | Subrahmanyam Jonnavittula (sj896b) Kris Hubble (wh4355) | Ed Berberich (eb1847) | 1/17: Project is still on hold but waiting on LPM to get the hold lifted. 1/9: Eric sent Q to Subra asking if hold is lifted. Subra is still working with LPM on lifting the hold. 11/20: Subra sent email stating that this project is on hold until further notice. 11/20: Kshama started working on DM 0378 but will NOT submit to the DBAs for materialization since the project is now on hold. 11/20: Eric provided more clarification to Kshama on this story. 11/16: Assigned to Kshama via Q 11/15: Need to start the work. Manish informed Eric via Q to assign this to other developer. 11/6: This work will be done in 1802 since it came in late and cannot be included in the 1711 deployment. 11/6: Manish needs to create a new DM to add FUNC_CODE to the tables. This will most likely be deployed in 1712 since it's too late for 1711 deployment. 11/3: Eric created the tasks in TDP today 10/31: Hong Wang provided the file layouts. Srinivas sent them to Manish 10/30: Eric attended Ed's story review. Need to find out and let Ed know if this is TO or code impacting.
1702 | 294010 | ?? | 1610 ALU Critical Features Project (BSS TD) 1702 delivery | VoIP |  |  | Cancelled | Eric | Cancelled | Cancelled |  | Kris Hubble (wh4355) | Kris Hubble (wh4355) | Didi Xie (dx080q) | 11/8: iPOR shows this project as being cancelled 10/13: Eric found this project in a permanent scrum call email that Srinvias forwarded. Eric found the below info on this project in an email from Jane Eisenmann. 292895– Tektronix Geoprobe .15.2 SW Release Upgrade / Ching-Chyuan Shieh Request Status: 8/29 No change. 8/22 – move to 17.04 release. Yet to be Evaluated. need module estimate details in iPOR. (?? PW Dev ) J. Eisenmann | Cancelled
1702 | 289834 | 457489 | USP virtual Charge Control Function (vCCF) BNS IT | VoIP |  |  | Code | Eric | Cynthia (DMaaP/DMD, DM, MD) Alan (KPI engine) | IT1 10/28/2016 - 11/18/2016 IT1 10/19/2016 - 12/9/2016 IT1 12/10/2016 - 12/30/2016 |  | Kris Hubble (wh4355) | Kris Hubble (wh4355) | Jeff Stein (js3831) | 10/13: Eric found this project in a permanent scrum call email that Srinvias forwarded. Eric found the below info on this project in an email from Jane Eisenmann. 289834 – USP virtual Charge Control Function (vCCF) BNS IT / Jeff Stein PENDING - Requirements Status: 10/3 Child user stories started. 9/19 - Epics have been completed by Steve Stathos and reviewed by Jeff. They are in Rally in PMOSS_VOIP - Team Blue folder. Jeff will start writing user stories ASAP. Need modules estimates in iPOR. 8/29 No change. 8/22 - project scope still in flux. Need modules estimates in iPOR. (PMOSS VOIP 56, DCAE 101 PW Dev) K. Hubble
1704 | 289834-CO | 457489 | USP virtual Charge Control Function (vCCF) BNS IT | VoIP |  |  | Code | Eric | Senthil (DMD, DM) | IT1 01/18/2017 – 02/07/2017 IT2 02/08/2017 – 02/28/2017 IT3 03/01/2017 – 03/21/2017 IT4 03/22/2017 – 04/11/2017 IT5 04/12/2017 – 05/02/2017 IT6 05/03/2017 – 05/23/2017 |  | Kris Hubble (wh4355) | Kris Hubble (wh4355) | Didi Xie (dx080q) | 2/1: Cynthia, Srinivas, Yeab & Eric attended the kickoff call today. The EPICs will be reviewed later today. 1/26: Kris Hubble invited Eric & Srinivas to discuss this project on 2/1. Eric will assign this to himself in iPOR
1702 | 283368A | 450044 | International Routing Consolidation for Agile Applications Part - A | VoIP |  |  | Code | Eric | Wes (DMD, DM, MD) Riya (DM, MD) | IT1: 10/25/2016 - 11/15/2016 IT2: 11/16/2016 - 12/6/2016 IT3: 12/7/2016 - 12/27/2016 |  | Jane Eisenmann (je3134) | Jane Eisenmann (je3134) | Ming-Ming Yu (my2263) | 11/3: Eric attended the US grooming session but he needs to work on the US tasks first before he can agree to the iteration and storypoint sizine. 10/24: Eric and Wes attended the US review session today
1704 | 284146 | 459054 | (VIP) IP IC: AVOICS/BVoIP Interop and Transit | MOBILITY |  |  |  | Dana | Srinivas | [5 empty] | 4/21: This rows was added by Srinvas. Used to add 2 tables (WPR) for APPDATASTATS - 284146 - 17.04 Per Tony Colon (Srini's note)
1707 | 284146 | 459054 | (VIP) IP IC: AVOICS/BVoIP Interop and Transit | VoIP |  |  | Code | Eric | Nag (DM) Kshama (DMaaP, DM, MD, KPI) Jerome (DMaaP) Wes (DM, MD) | This IT schedule is NOT being used anymore IT1 01/18/2017 – 02/07/2017 IT2 02/08/2017 – 02/28/2017 IT3 03/01/2017 – 03/21/2017 IT4 03/22/2017 – 04/11/2017 IT5 04/12/2017 – 05/02/2017 IT6 05/03/2017 – 05/22/2017 New HALO schedule to use IT0 - 01/16/2017 – 02/10/2017 IT1 – 02/13/2017 – 03/10/2017 IT2 – 03/13/2017 – 04/07/2017 IT3 – 04/10/2017 – 05/05/2017 |  | Jane Eisenmann (je3134) | Jane Eisenmann (je3134) | Didi Xie (dx080q) | 1/13: Wes & Eric attended the US review session today. 1/6: Jane informed Eric of this project that will have the US reviewed on 1/13 by Didi Xie | All DMs have been materialized and project is ready to deploy.
1710 | 283554D | 464501 | (VIP) IP IC Wholesale VoLTE CVOIP 2 - Phase 5 | ? |  |  | Cancelled | Eric | Wes (DM) |  |  | Subrahmanyam Jonnavittula (sj896b) | Subrahmanyam Jonnavittula (sj896b) | Saxena Deepa (ds521a) June Shi (ys1362) | 3/29: Wes informed Eric of this project during a status call. Didi moved a 284146 Metaswitch story to this project. | Cancelled
1707 | 283368 | 448567 | (VIP) International Routing Consolidation - Part A | VoIP |  |  | Code | Eric | Sachin (DM, MD) Gourav (DM, MD) Prasad (DM, EE) Wes (DM, MD, EE) | IT1 01/18/2017 – 02/07/2017 IT2 02/08/2017 – 02/28/2017 IT3 03/01/2017 – 03/21/2017 IT4 03/22/2017 – 04/11/2017 IT5 04/12/2017 – 05/02/2017 IT6 05/03/2017 – 05/23/2017 |  | Jane Eisenmann (je3134) | Jane Eisenmann (je3134) | Ming-Ming Yu (my2263) | 1/17: Srinivas and Eric attended the US review session today for this US. 1/16: Will be reviewed on 1/17. Riya has been invited since it's a morning US review. | All DMs have been materialized and project is ready to deploy.
1507 | 279581d | 443057 | MCR R2b Cloud Foundry correct WBS | MCR (Core Services) |  |  | Code | Fani
1510 | 283427 | 445690 | AIC Development - ECOMP - Sub-project: DCAE Platform | MCR (Core Services) |  |  | Code | Fani |  |  |  | Weili Wang (ww352v) |  |  | 9/28: Data loading problems and Wes is loading the new data files that have been corrected. Same file name is being resent so loading this file requires manual execution of the load.
1512 | 287704-14 | 445690 | AIC Dev/ECOMP ¿ DCAE Platform | MCR (Core Services) |  |  | Code | Eric / Fani | Srinivas Wes | SP 1: 10/5-10/16 SP 2: 10/19-10/30 SP 3: 11/2-11/13 (IST & ETE) SP 4: 11/16-11-27 (Defect only << Final ETE) |  | Weili Wang (ww352v) | Amar Gurajapu (ag753n) | Leo Xu (x2168)
1510 | 283427 | 445690 | AIC Development - ECOMP - Sub-project: DCAE Platform | Gamma |  |  | Code | Fani | Srinivas Binesh Bharat Jerry Drottar |  |  | Weili Wang (ww352v)
1512 | 287704-10 283427-10 (old PID) | 445690 | AIC Development - ECOMP - Sub-project: DCAE Platform | Gamma |  |  | Code | Fani | Srinivas Binesh Bharat Jerry Drottar | SP 1: 10/5-10/16 SP 2: 10/19-10/30 SP 3: 11/2-11/13 (IST & ETE) SP 4: 11/16-11-27 (Defect only << Final ETE) |  | Weili Wang (ww352v) | Latha Singanamalli (ls897x) Robert Lynch (rl1748) | Joe Chou (jc2723) Hui-Tung Yang (hy588a)
1512 | 287704-11 | 450735 | AIC Dev/ECOMP - DCAE Platform | Gamma |  |  | Code | Eric | Chris Mengle | SP 1: 10/5-10/16 SP 2: 10/19-10/30 SP 3: 11/2-11/13 (IST & ETE) SP 4: 11/16-11-27 (Defect only << Final ETE) |  | Weili Wang (ww352v) | Swati Chauhan (ss3064) | Ken Martau (km1785) +T26
1512 | 285914 | 449762 | ATT Switched Ethernet Network On Demand Phase 7 | Gamma |  |  | Code | Eric / Fani | Srinivas | SP 1: 10/5-10/16 SP 2: 10/19-10/30 SP 3: 11/2-11/13 (IST & ETE) SP 4: 11/16-11-27 (Defect only << Final ETE) |  | Weili Wang (ww352v) Kathleen Liu (dl1548) | Robert Lynch (rl1748) | Alan Gale (ag9241)
1602 | 287301 | 450920 | uCPE Procurement Automation - JDM monitoring 16.02 | Gamma |  |  | Code |  |  |  |  | Weili Wang (ww352v) |  | Sanjini George (sg5265)
1604 | 288255 | 452508 | Network Functions on Demand Features – 1604 release | Gamma |  |  | Code | Eric |  | SP 1: 1/25/2016-2/5/2016 SP 2: 2/8/2016-2/19/2016 SP 3: 2/22/2016-3/4/2016 SP 4: ?? (IST & ETE) SP 5: ?? (Defect only << Final ETE) |  | Weili Wang (ww352v) | ?? | Alan Gale (ag9241)
1604 | 283988A | 452444 | vPE for MoW AVPN - Instantiation | Gamma |  |  | Code | Eric & Johan |  | SP 1: 1/25/2016-2/5/2016 SP 2: 2/8/2016-2/19/2016 (Dev) SP 3: 2/22/2016-3/4/2016 (IST) SP 4: 3/7/2016-3/18/2016 (IST & ETE) SP 5: 3/21/2016-4/1/2016 (ETE) SP 6: 4/4/2016-4/15/2016 (DG & Prod Prep) |  | Swati Chauhan (ss3064) Kurt Smith (ks7543) Jane Chung (jc1858) | Swati Chauhan (ss3064) Kurt Smith (ks7543) | Alan Gale (ag9241) Jeff Yu (jy6277) Lian-Tay Shiang (ls895q) | 1/27: Here is the summary of this brand new project. It seems to be related to the vRR project. Lian-Tay Shiang (ls895q) had a project estimate and 1604 acceptance call today. The project is NOT in Rally yet. Below is what VETL/Vertica will need to do in this project but we may just be TSO. VETL/Vetica will need to receive Juniper vPE (Virtual Provider Edge) MX86 PM alerts via UEB. This may be TSO. Eric asked "Are the UEB vPE PM alerts coming under the "PMOSS-PERFORMANCE-ALERTS" topic? If so, then this would be TSO." Waiting for answer from Lian-Tay. Lian-Tay will gather the UEB topics for this vPE data by EOB tomorrow (1/28) to determine if it’s truly TSO or if it is code impact for VETL/Vertica. 1/15: Weili informed us that this is a new project coming in. New project coming in. No US's have been created yet and no ETA as of today on the US creation.
1607 1604 | 288361 | 452738 | NFoD Phase 9 VNF features : 1604 Release | Gamma |  |  | Code | Eric | DM/MD: Cynthia | SP1: 1/25/2016-2/5/2016 SP 2: 2/8/2016-2/19/2016 SP 3: 2/22/2016-3/4/2016 |  | Weili Wang (ww352v) | ?? | Alan Gale (ag9241) Stephen Lam (sl679r) | 3/8: All VETL/Vertica work was completed in 1604. 3/3: Moved from 1604 to 1607.
1604 | 289047 | 453372 | Closed Loop ECOMP 162 | Gamma |  |  | No impact | Dana | Deployed | SP 1: 1/25/2016-2/5/2016 SP 2: 2/8/2016-2/19/2016 (Dev) SP 3: 2/22/2016-3/4/2016 (IST) SP 4: 3/7/2016-3/18/2016 (IST & ETE) SP 5: 3/21/2016-4/1/2016 (ETE) SP 6: 4/4/2016-4/15/2016 (DG & Prod Prep) |  | Weili Wang (ww352v) | Amar Gurajapu (ag753n) | Hui-Tung (hy588a) | 2/18: Dana confirmed today that there is NO impact to VETL/Vertica. We are not TSO either. Dana(9:57:38 AM): hey when you get a chance...you have the status file open... 289047 is no impact to vETL/Vertica Dana(9:57:43 AM): i finally got an answer Eric(9:58:13 AM): TSO or no impact at all? Dana(9:58:23 AM): no impact at all Dana(9:58:35 AM): it was covered in another project... Dana(9:58:41 AM): let me get the PID for you Dana(10:00:36 AM): No impact per WS4361; covered under Skyfall: US 573651 and vUSP: US 597777 (marked as TSO) 2/10: Hui-Tung had a US review call today but since Dana is the iPOR dev lead then I (Eric) did not attend. .
1607 | 289116 | 454398 | Network Functions on Demand - 1607 Release | Gamma |  |  | Code | Eric | DM/MD: Cynthia | SP 1: 3/6/2016-3/19/2016 (Dev) SP 2: 3/21/2016-4/1/2016 (Dev) SP 3: 4/4/2016-4/15/2016 (Dev) SP 4: 4/18/2019-4/29/2016 (Dev) SP 5: 5/2/2016-5/13/2016 (Dev) SP 5: 5/16/2016-5/27/2016 (Dev) |  | Weili Wang (ww352v) | ?? | Alan Gale (ag9241) Stephen Lam (sl679r) | 5/4: A new US is going to be created by Stephen Lam today for a brand new Juniper table (UCPE_JNX_COS) to store uCPE & Shell QOS data. Dev work is due 5/13. 4/5: All VETL/Vertica work is complete 3/7: Eric was informed by Weili & Stephen Lam that this US review session will take place this week.
1607 | 283988B | 454155 | vPE for MoW AVPN - Instantiation 1607 (WIPM) | Gamma |  |  | Code | Eric | DM/MD: Brett | IT 14: 5/9/2016-5/27-2016 IT 15: 5/30/2016 – 6/10/2016 IT 16: 6/13/2016 – 7/8/2016 |  | Kurt Smith (ks7543) | Kurt Smith (ks7543) | Jason Chou (jc340x) | 5/9: Eric reviewed the 2 Uss and assigned them to Brett. Eric created the US tasks in Rally. 5/4: Johan attended on Eric's behalf the US review meeting today since Eric had to attend a mandate QH review at the same time. 3/15: Tony assigned this project to Eric via the AM status call.
1607 | 284581 | 452276 | Skyfall Wi-Fi Calling (Play 3) - BNCS-IT (this project has a dependency on project 284249) | PMOSS VoIP |  |  | Code | DANA | Wes Cynthia |  |  | Jane Eisenmann (je3134) |  | Jeff Stein (js3831) | 3/15: Tony assigned this project to Dana via the AM status call. Johan says this "was" TSO but Tony says iPOR shows code impact 3/1: Johan attended initial overview of project and initial US review.
1607 | 283988B | 454155 | vPE for MoW AVPN - Instantiation 1607 (Compass) | Gamma |  |  | No impact | Eric | DM/MD: Srinivas | R02.2 2016-04-19 - STD 3w: 3/30/2016-4/19/2016 R02.3 2016-05-10 - STD 3w: 4/20/2016-5/10/2016 R03.1 2016-05-31 - STD 3w: 5/11/2016-5/31/2016 R03.2 2016-06-21 - STD 3w: 6/1/2016-6/21/2016 R03.3 2016-07-12 - STD 3w: 6/22/2016-7/12/2016 |  | Jane Chung (jc1858) Swati Chauhan (ss3064) | Jane Chung (jc1858) Swati Chauhan (ss3064) | Jeff Yu (jy6277) | 4/26: vETL/Vertica, No longer code impacted, QOS work was removed. From Jane Chung's status email 4/26 - "Short summary for managers: Descope QoS and only keep WBG report. (Target QoS by VEC for future release.) (And so now no code impact for modules – Compass Collector, Vetl/Vertica, DMD.)" 4/26: VETL/Vertica descoped from this project. 4/26: Jane mentioned that ALL the DMD and vPE Juniper QoS PM may be descoped. 3/15: Tony assigned this project to Eric via the AM status call.
1607 | 288733 | 454546 | L0/L3 SDN - Centralized Tunnel Management of CBB on CRS | Gamma |  |  | Code | Sudhakar | DM/MD (PM): Srinivas | SP 1: 4/18-4/29 SP 2: 5/2-5/13 |  | Weili Wang (ww352v); Jane Chung (jc1858) | Amar Padmesh Gurajapu (ag753n) | Alan Gale (ag9241) Stephen Lam (sl679r) | 3/22: Eric attend the 1st US review session but Stephen was trying to just get a head start on the creation of the US. These Uss are NOT near final and Stephen will have a regular US review session later after he solidifies the Uss. 3/15: Tony assigned this project to Eric via the AM status call.
1607 | 288255a | 455490 | 1610 - NoD scope fallout from 1604 release | Gamma |  |  | TSO | Eric |  |  |  | Weili Wang |  |  | 4/22: Eric discovered this project in iPOR assigned to him. It is marked as "Testing Only".
1610 | 290312 | 457896 | MP00002107 Network on Demand Hybrid VPN | Gamma |  |  | Code | Eric | Jerome (DMaap) Cynthia (DM/MD) | IT4 07/11/2016 - 07/22/2016 IT5 07/25/2016 - 08/05/2016 IT6 08/08/2016 - 08/19/2016 IT7 08/22/2016 - 09/02/2016 |  | Weili Wang (ww352v) | Weili Wang (ww352v) | Zosim Kanevsky (zk2547) Stephen Lam (sl679r) | 6/23: Weili Q'd Eric and said that Eric is assigned to this project. Weili said the US reviews will take place on 6/24. Since Eric is on vacation on 6/24 then Cynthia will attend the US review meeting. | 9/26 Cynthia: ST in progress 9/28 Eric: Project is ready for deployment
1702 | 290312A | 461053 | Network on Demand Hybrid VPN-1610 Fall Out | Gamma |  |  | Code | Eric | Cynthia (DM/MD) |  |  | Weili Wang (ww352v) | Weili Wang (ww352v) | Ted Xia (tx541d) | 10/2: Weili informed Eric via her other scrum call that this project is coming and will be code impacting for VETL/Vertica (new tables) | 9/26 Cynthia: ST in progress 9/28 Eric: Project is ready for deployment
1610 | 290789 | 457624 | MP00004193 NFoD uCPE Release 1610 | Gamma |  |  | Code | Eric | Wes & Abhishek (DM, MD) | IT5 07/25/2016 - 08/05/2016 IT6 08/08/2016 - 08/19/2016 IT7 08/22/2016 - 09/02/2016 |  | Weili Wang (ww352v) | Weili Wang (ww352v) | Stephen Lam (sl679r) | 6/23: Weili Q'd Eric and said that Eric is assigned to this project. Weili said the US reviews will take place on 6/24. Since Eric is on vacation on 6/24 then Cynthia will attend the US review meeting. | 9/28 Eric: Project is ready for deployment
1610 | 288487 | 457896 | Deconstructed ROADM / Metro DWDM (1) (Play 1) | ?? |  |  | ?? | Brij | N/A |  |  | Weili Wang (ww352v) | Steve Delgado () | Charles Pittman () | 7/11: Tony assigned this project to Brij. 7/6: Weili mentioned a new Layer 3 type project but it is not a Gamma project. Eric told Weili to ask Tony who will be assigned to this project.
1702 | 292589 | 459168 | Network on Demand Hybrid VPN | Gamma |  |  | Code | Eric | Cynthia (DMaaP/DM/MD) | IT1 10/24/2-16 - 11/04/2016 IT2 11/07/2-16 - 11/18/2016 IT3 11/21/2016 - 12/2/2016 IT4 12/5/2016 - 12/16/2016 |  | Weili Wang (ww352v) | Weili Wang (ww352v) | Ted Xia (tx541d) | 9/30: Eric provided dev size estimates below back to Weili. Got confirmation from Tony via Q. 4 person weeks will be needed for the items listed below Topic subscription including DIT and ST HO New table to store messages if needed including DIT and ST HO US reviews, grooming, meetings, questions, etc Deployment
1610 | 291013 | 457794 | Closed Loop ECOMP 164 | ECOMP |  |  | Code | Eric | Jerome (DMaaP/DMD) Pope (DMaaP/DMD) Yeab (DMaaP/DMD) Alan (MD) Srinivas (MD) | IT1 05/30/2016 - 06/10/2016 IT2 06/13/2016 - 06/24/2016 IT3 06/27/2016 - 07/08/2016 IT4 07/11/2016 - 07/22/2016 IT5 07/25/2016 - 08/05/2016 IT6 08/08/2016 - 08/19/2016 IT7 08/22/2016 - 09/02/2016 IT8 09/05/2016 - 09/16/2016 |  | Weili Wang (ww352v) | Swati Chauhan (ss3064) | Wen Shang (ws4361) | 6/23: Weili Q'd Eric and said that Eric is assigned to this project. Swati's scrum call will review 291013 US | 9/28 Eric: DIT for DMaaP topic subscriptions is pending. Plus, Pope & Jerome are still working on implementing the DMaaP onboarding process and should complete this by 9/30
1702 | 293908 | 461364 | Closed Loop ECOMP 171 | ECOMP |  |  | Code | Eric | Nag (DMaaP DR, DM, MD) Jerome (DMaaP mentor) Manish (DMaaP mentor) | IT1: 10/24/2016 - 11/04/2016 IT2: 11/07/2016 - 11/18/2016 IT3: 11/21/2016 - 12/02/2016 IT4: 12/05/2016 - 12/16/2016 IT5: 12/19/2016 - 12/30/2016 IT6: 01/02/2017 - 01/13/2017 |  | Swati Chauhan (ss3064) | Swati Chauhan (ss3064) | Nasreen Habib | 11/7: Nasreen held a US review session for VETL/Vertica. She still needs to finalize the 2 USs with Alan (KPI) and Srinivas (tables). 10/27: Nasreen Habib & Sunil Yerra held a meeting today to discuss vUSP Juniper DBE DKaT KPI and alerts via topic DCAE_EA_KPI_RSLTS. They did not get to the VETL/Vertica Uss.
1512 | 276431 | 442430 | Federation Service (UC) | Fdr Svc |  |  | Code | Fani | Srinivas Binesh Bharat Huei Vishal Johan | N/A |  | William Kris Hubble (wh4355) |  | Fil Deguzman (fd2432) | DIT 11/9-11/20 & handoff to ST is 11/11. WBG need 5 views (1 base, 1 count, 3 signature) layouts by 9/30. Waiting on Bharat and Binesh to produce a Word doc of the 5 custom views to be completed by 9/30 and will send to Srini/me for review.
1607 | 283988 | 454155 | vPE for MoW AVPN | Gamma |  |  | No impact | Eric |  | ?? |  | Jane Chung (jc1858) Swati Chauhan (ss3064) | ??+N36K36:E36:T36 | Jeff Yu (jy6277) | 4/25: Eric checked iPOR and there is no VETL/Vertica impact in this project. 3/15: Tony assigned this project to Eric via the AM status call.
1610 | 283552 | 447996 | Next Gen Virtual Route Reflector Rel. 2 | PMOSS_COMPASS |  |  | Code | Brij | Dev Lead: Srinivas DM/MD : Zhenyuan | ?? |  | Jane Chung (jc1858) | Jane Chung (jc1858) | Jeff Yu (jy6277) | 3/15: Tony assigned this project to Brij & Huei via the AM status call. | Brij: ST in progress
1607 | 289359 | 455333 | 32 - Telecom Spend - SI 37106 - 32.1 |  |  |  | Code | Brij | DMD: Wes PM: Srinivas CTI: Wes TCA (TSO): Srinivas | SP 1: 4/11-5/6 SP 2: 5/9-6/3 |  | Soumya Jagadish Kumar (sj650a) | Soumya Jagadish Kumar (sj650a) | Jeff Yu (jy6277) | 4/21: Eric just found this project today assigned to Brij via Tony's project assignment spreadsheet. Brij will update all the required info on this project
1602 | 286074 | 450765 | NetBond Expansion - Features & Footprint - QoS Premium Tier Release 1 | Netbond |  |  | Code | Huei | Heui Jerome Srinivas Chris C Zhenyuan Binesh | SP1 (284862a) 11/23-12/18 SP2 (284862a) 12/21-1/15/16 SP3 (284862a) 1/18-2/12/16 SP4 (284862a) 2/15-3/11/16 SP5 (284862a) 3/14-4/08/16 Release 4/16-4/17/16 |  | Kurt Smith (ks7543) |  | Kushal Jain (kj7330)
1611 | 284331f | 458542 | NextGen NBFW October Release | PMOSS_COMPASS |  |  | Code | Brij | Dev Lead: Srini DMD: Yeab DM/MD: Bhanu |  |  | Jane Chung (jc1858) | Jane Chung (jc1858) | Jeff Yu (jy6277) | 7/28: We were told, it is big. VEC is still in design. VEC has issues with collection.
1610 | 283988c | 456015 | vPE for MoW AVPN - Release 4 | PMOSS_COMPASS |  |  | Code | Brij | Dev Lead: Wes DMD: Wes/Yeab DM/MD: Wes |  |  | Jane Chung (jc1858) | Jane Chung (jc1858) | Jeff Yu (jy6277) | 8/18: Eric noticed this project being mentioned in the team chat window and Yeab stated that It's assigned to Brij
1605 | 287297 | 452219 | NetBond Expansion - Features & Footprint - QoS Premium Tier Release 2 | Netbond |  |  | Code | Eric | DM/MD: Huei (All US except for 1) SUM: Srinivas/Zhenyuan (1 US) | IT 33: 3/17/2016-3/30/2016 IT 34: 4/7/2016-4/27/2016 IT 35: 4/28/2016-5/18/2016 |  | Kurt Smith (ks7543) |  | Kushal Jain (kj7330) | 4/25: This one is being worked on, but Srinivas is working on 2 hourly summaries. 3/9: Eric, Huei & Srinivas attended the Rally US review session. Eric will add all the USs to this file today. 3/7: Eric asked Kushal (kj7330) if he created the USs in Rally and he has not. He will create them on 3/8 and review them with the team on 3/9. 3/2: Eric & Huei attend the final US review session today. Kushal will create the USs in Rally today (3/2). Eric will provide the updated notes over to Huei for her to review and discuss. Eric told Kushal to move all aggregation USs to the next iteration and he agreed. 2/25: Eric attended the 2nd US review session today. The notes that Eric took are in the US task desription column for now. The USs have NOT been created in Rally yet. Eric sent the notes to Kushal to confirm that they are complete and accurate. Waiting on Kushal to confirm. 2/24: Eric attended the 1 US review session. We have no choice but to deliver this project in 1605. 2/15: Eric Qd Kurt on this project. Below is the current status. US grooming session will be on week of 2/22. Eric(9:08:30 AM): Hi Kurt. Huei is on the 288288 (NetBond Expansion - Features & Footprint - Advance Rate Management R1) project but iPOR still says that this project is PENDING. It's been in that state for over 1 month now. Any news on this project? Kurt(9:56:20 AM): Hi Eric - 288288 (16.07) is dependent on delivery of 287297 (16.04) which had to be resolutioned because the solution architects could not agree on a design... we are going into our 4th week with defining the final solution for 287297 which has Vertica/Vetl impacts... Kurt(9:57:03 AM): 287297 is the one that you need to keep on your immediate radar... since this is currently a 16.04 delivery Kurt(9:58:16 AM): but, we need to determine if when we can deliver in 16.04 but I would push for 16.05 Kurt(9:59:00 AM): But, for 288288, the final design will be determined by what we deliver with 287297 Eric(9:59:24 AM): Ok, so I should track 287297 (1604) and NOT 288288 (dependent on 287297). When is the US grooming or review session going to be held? Kurt(10:01:16 AM): Hopefully, early next week... if they can agree on the final solution early this week... but I estimate we will have our review of User Stories about a week after the final solution is baselined Kurt(10:02:11 AM): 288288 wants us to deliver in 16.05 or 16.06 Kurt(10:02:32 AM): but I am pushing back because of the dependency... Eric(10:03:10 AM): Ok, then doing 287297 in 1604 is going to be very tight so 1605 may more realistic. We'll see the amount of VETL/Vertica work in 287297 during the US grooming session and go from there. Kurt(10:03:19 AM): But, because this is Netbond... we probably will be still held to deliver 287297 in 16.04 Eric(10:03:28 AM): Kurt(10:04:59 AM): then, we want to deliver 284862a in 16.04 which has Vertica/Vetl impacts... but this PID may get cancelled and we have to retarget this work Eric(10:06:20 AM): 284862a was cancelled... Eric(10:06:26 AM): already Kurt(10:12:26 AM): Ah cool... then I need to talk to Kushal about what the game plan is for this work Eric(10:31:32 AM): Disregard my Q about 284862a being cancelled. See below. Huei(10:29:43 AM): Eric(10:06:20 AM): 284862a was cancelled already -- it was cancelled for COMPASS but the one Kurt mentioned is under CUR/WUR same project # but different app Eric(10:30:53 AM): Hmm, ok, I'll let Kurt know. This is so confusing... Eric(10:32:01 AM): Huei(10:31:35 AM): the one got cancelled was under Jane Chung, feed provided by Su-Lin it got cancelled after we did the ST HO Eric(10:31:54 AM): Ok thanks 1/27: Eric or Johan to find out from Kurt Smith the dates for this project. 1/11: Huei mentioned this project that is in pending status and still gather requirements in iPOR. Will need to gather requirements when they are ready.
1607 1606 | 288288 | 451342 | NetBond Expansion - Features & Footprint - Advance Rate Management R1 | Netbond |  |  | Code | Eric | DM/MD: Huei, Zhenyuan DMD/DMaaP: Jerome (Srinivas as B/U) | IT 33: 3/17/2016-3/30/2016 IT 34: 4/7/2016-4/27/2016 IT 35: 4/28/2016-5/18/2016 IT 36: 5/19/2016-6/8/2016 |  | Kurt Smith (ks7543) |  | Kushal Jain (kj7330) | 4/25: Dev due date is 5/17 due to possible escalations. 4/25: Might get pushed to another release, but likely not - work as it is 16.07. We have the layouts, but don't work on it yet (PENDING real-time requirement issue to be resolved). This project is dependent on 287297 1/11: Huei mentioned this project that is in pending status and still gather requirements in iPOR. Will need to gather requirements when they are ready.
1607 | 288248 | 454385 | Mandate P1542 - German Customer Data Privacy (Compliance Finding) | Gov Mandate |  |  | Code | Eric | DMaap: Yeab DM/MD: Huei | IT 33: 3/17/2016-3/30/2016 IT 34: 4/7/2016-4/27/2016 IT 35: 4/28/2016-5/18/2016 IT 36: 5/19/2016-6/8/2016 IT 37: 6/9/2016-6/29/2016 IT 38: 6/30/2016-7/20/2016 |  | Kurt Smith (ks7543) |  | Kushal Jain (kj7330) | 5/2: The work in this project was assigned to IT 37 4/28: Eric & Johan attended this US review. Nobody is assigned to this project in iPOR. New VETL to Dmaap interface needs to be written. 4/21: Eric found this in Tony project assignment file. His file does NOT have an iPOR Dev Lead assigned to it yet.
1512 | 283151 | 447129 | LTEC Roadmap (LTE VQoS NetOps Reqt) | Sundance | [10 empty] | No development for VETL in this project. This PID is only here because we can charge to this PID for the work being done in QH-MS-151211 for release 15.12.
1512 | QH-MS-151211 285500 & 283151 | 447129 | Affirmed Sundance VM Uptime measurements | Sundance |  |  |  | Johan | Chris Carr | Load 1 file from PEC Create 1 table Create 1 custom view |  |  |  | Fani Popovici | 11/2: Chris is waiting for the Erwin license file. Will be working on the DM (1 table & 1 custom view) & metadata this week.
1604 | QH-MS-160202 285500 / 285809 | 449845 / 449814 |  | Sundance |  |  | Code | Jerome Srinivas | Jerome Srinivas Bharat Tolani |  |  | Terri Marhoffer (tm3178) |  | Willa Ehrlich (we1519)
1607 | 290348 | 454273 | ECOMP Policy Operational 163 | DCAE |  |  | Code | DANA | Canceled |  |  | WANG, WEILI |  | CORRADO, CHRISTEN M ​ | 3/31: Shows as CANCELED in PRISM
1602 | 284672 | 450122 | Neo 6.0 (Play 1) & Neo 7.0 (Play 1) | DCAE |  |  | Code | Jerome | Jerome |  |  | Terri Marhoffer (tm3178) |  | Justine Lau Rama Ati (RA698M)
1604 | 282717 | 448460 432271 | Skyfall - Cricket Classic | Skyfall |  |  | Code | Eric or Johan | Jerome | IT2: 12/14 - 01/01 (no VETL dev) IT3: 01/04 - 01/22 IT4: 01/25 - 02/12 IT5: 02/15 - 3/4 IT6: 03/07 - 03/25 (E2E, UAT) Deploy: 4-8 |  | Rick Gilormo (RG1854) | Latha Singanamalli (ls897x) | PMOSS-Mobility: LAU, JUSTINE jl905g@att.com; POSADAS, AMANDA ap919e@att.com MSTR: JOSHI, AJAY S aj8568@att.com; YERRA, SUNIL sy175s@att.com WBG: TANG, CHAOJUNG ct2963@att.com
1607 | 289924 | 455608 | Closed Loop ECOMP 163 | DCAE |  |  | Code | DANA | In Progress (Srinivas) |  |  | WANG, WEILI |  | SHANG, WEN
1607 | 289923 | 455911 | Hardware Ingest ECOMP 163 | DCAE |  |  | Code | DANA | In Progress (Srinivas) |  |  | WANG, WEILI |  | SHANG, WEN
1605 1604 | 287761 (Dependent on vMMSC 282886) | 450771 | MOG 1.0 (Dynamic Policy Control and Charging Infrastructure) | vMOG 1.0 |  |  | Code | Johan |  | SP1: 2/1/2016-2/19/2016 SP2: 2/22/2016-3/11-2016 SP3: 3/14/2016-4/1/2016 IST: ?? ETE: ?? |  | Terri Marhoffer (tm3178) | Janet Perrineau (jp6581) Latha Singanamalli (ls897x) | Justine Lau (jl905g)
1605 1604 | 282886 | 451113 | Mobility NSD - Sustaining - MMS Virtualization BNS IT | vMMSC |  |  | Code | Eric | Huei Zhenyuan Yeab Brett Jerome | N/A |  | Terri Marhoffer (tm3178) | ?? | Ramamurthy Ati (ra698m) | 3/18: Terri informed Eric that this is now a 1605 project. Eric to get more details on that. The new deloyment date is 5/21
1602 | 288149 | 451158 | AIC Development ECOMP Guided Design | D2 eComp |  |  | Code | Eric & Johan | Jerome | IT25: 11/30/2015-1/7/2016 IST: 1/15/2016-1/22/2016 ETE: 1/29/2016-2/12/2016 |  | Bryan Sokolik (bs4282) | ?? | Leo Xu (lx2168)
1602 | 288139 | 451852 | AIC Development ECOMP Common Platform 16 1 | D2 eComp |  |  | Code | ?? | ?? | SP6: 1/18/2016-1/29/2016 |  | Weili Wang (ww352w) | ?? | ?? | 3/21: Eric checked iPOR to see who was assigned to this project and nobody is yet. This project is listed in iPOR as "Yet to be evaluated"
1607 | 283878 | 451362 | MP Core Part 3: HSIA By-Pass Feature | ?? |  |  | Code | Johan |  | ST HO: 5/16 |  | Kris Hubble (wh4355) | Kris Hubble (wh4355) | Rick Quagliata (rq2591)
1605 | 285097A | 451747 | MOW IP Flex MFA (R2 3) Phase 2 | PMOSS VoIP |  |  | No impact | Johan | ?? | N/A |  | Jane Eisenmann (je3134) Kris Hubble (wh4355) | ?? | Kin Wong (kw5238) | 12/5: See Qs from Tony FROM 12/5. This project wasn't assigned to a lead developer (Johan, Eric or Dana) by Tony nor in iPOR. VETL/Vertica is NOT impacted in this project. Waterfall Project: Notes from Ravi: 285097a - has some changes to CTI feeds, but new columns added are not required in Vertica, and file has header, so VETL will ignore them, we are test impact only.
1604 | 289045 | 454323 | Hardware Ingest ECOMP 162 | ?? |  |  | Code | Eric & Johan | ?? | ?? |  | Brett Dickson | ?? | Wen Shang (ws4361) Minsky Luo (ml106g) | 4/4: Done via CR141957 3/2: Eric attended the 2nd meeting to determine if the project is doable for 1604. The client (Raja Gunasekaran rg6282) said they'll try to push the work to 1607. Eric provided the below to Tony: It is NOT doable since USs are not yet written. It will take time to solidify the USs and ensure that the full scope of the US work is understood and there won’t be much time left for development. Plus, we CANNOT begin working on the tables until the SE (Wen Shang) provides the table layouts. VETL work: • Load ceilometer, broadworks & A&AI inventory datasets into ~15 existing tables in Vertica o The tables already exist today w/o any data in DCAECOMMON & BSXBWORK_VIEWS schemas • Add 2-3 new columns (ex. DATETIME) into ~34 existing ceilometer, broadworks & A&AI tables • Add ~30 new counters into ## new or existing Ericsson vSBG PM tables based on table layouts from Wen Shen (SE)
1607 | 288228 | 452794 | USP pCCF 30.3 HP G8 |  |  |  | TSO | Eric |  |  |  | Kris Hubble (wh4355) | Kris Hubble (wh4355) | Didi Xie (dx080q) | 3/24: Johan and Srinivas attended the initial US review today. No coding for vETL/Vertica. Test support needed involving the CDR flow that was done in vUSP (284249) – need to test to ensure that only. Additional CDR data will come via existing files and topics as it was implemented in 284249, vUSP project.
288349
1610 | 283866 | 454883 | [5 empty] | Brij | N/A | [5 empty] | 7/28: No VETL/Vertica impact per iPOR. 4/21: Eric just found this project today assigned to Brij via Tony's project assignment spreadsheet. Brij will update all the required info on this project
1607 | 288348 | 452652 | Sundance 2.1 | PMOSS_Mobility |  |  | Code | DANA | Brett/Cynthia/Ravi 6/30: Cynthia will own Brett's deliverables for the release |  |  | Terri Marhoffer (tm3178) |  | POPOVICI, STEFANA A ​ | 6/29: All the code is in the 288236 objects. 4/7: Email to Fani to find out when file layouts will be available 3/17: Dana agreed to take this project from Eric 6/28: Ravi will be taking over this project from Brett for deployment support. Brett to roll off at the end of June.
1607 | 288236 | 452653 | ASE Europe Launch | PMOSS_Mobility |  |  | Code | DANA | Brett/Cynthia/Ravi 6/30: Cynthia will own Brett's deliverables for the release |  |  | Terri Marhoffer (tm3178) |  | PENG, JIYA | 4/7: File layout availability: File based tables design on 4/11; SNMP design – 4/25 3/2: Dana agreed via meeting to take this project 6/28: Ravi will be taking over this project from Brett for deployment support. Brett to roll off at the end of June.
1604 | 287570 | 451529 | Skyfall International Roaming Change Request - Network OSS | PMOSS_Mobility |  |  | Code | DANA | Cynthia |  |  | Rick Gilormo (RG1854) |  | Ram Iyer | 4/18: Ram said he forgot a few hierarchy entries; pending list from him
1702 1608 1607 | 284777 | 447590 | vVoicemail Platform Evolution | DCAE |  |  | Code | DANA | DM/MD: Cynthia DMD: Jerome KPI: Yeab |  |  | Rick Gilormo (RG1854) |  | Justine Lau | 1/13/17: Lab remains unavailable. May deploy in the "dark". 4/18: Wes may not be able to do this one. There is DMD work. vETL/Vertica work may not start until Iteration 2 because PEC will not have the layouts available. 4/7: US under review with SE 3/2: Dana agreed via meeting to take this project
1604 | 282055 | 443977 | Next Gen Virtual Route Reflector (VRR) | VRR Compass |  |  | Code | Eric | Johan Chris Char Jerome | SP1 (275349 & 282055) 11/30-12/25 SP2 (275349 & 282055) 12/28 - 1/22 SP3 (275349 & 282055) 1/25 - 2/19 SP4 (275349 & 282055) 2/22 - 3/18 SP5 (275349 & 282055) 3/21 - 4/15 Release 4/16 - 4-17 |  | Jane Chung (jc1858) |  | Jeff Yu (jy6277) Kapil Joshi (kj811t) Vinodh Pemmasani (vp663p) | ??
1607 | 282804 | 452050 | Skyfall VoLTE / Messaging Over IP | PMOSS VoIP |  |  | Code | DANA | Wes Cynthia |  |  | Jane Eisenmann (je3134) |  | Ming-Ming Yu (my2263) | 6/29: Code for this project has been wrapped in with 282804. 3/15: Tony assigned this project to Dana via the AM status call. 3/1: Johan attended initial overview of project and initial US review.
1607 | 287354 | 453328 | NextGen Platform for AVPN/VPLS/ Cloud/VOIP Services | PMOSS_WIPM |  |  | TSO | Brett | Brett |  |  | ?? Jane Chung ?? Maybe. Nobody listed in iPOR |  | Lian-Tay Shiang (ls895q) | 4/21: Eric found this in Tony project assignment file. His file does NOT have an iPOR Dev Lead assigned to it yet BUT iPOR shows Brett assigned as the iPOR Dev Lead.
1607 | 290330 | 455504 | ADIoD GA Blockers |  |  |  | Code | Ravi | DM (Reports): Ravi |  |  | Weili Wang (ww352v) | Weili Wang (ww352v) | Ed Gujju | 4/25: Not sure if Vertica will do the filtering or Microstrategy will do 4/21: Eric just found this project today assigned to Sudhakar via Tony's project assignment spreadsheet. Sudhakar will update all the required info on this project 6/28: VETL built SQLs for MSTR to embed in their reports. No VETL/Data Model work for this project, other than to support MSTR with report SQLs.
1607 | 285867B | 455982 455675 | Ericsson vMME Certification (NFV) | vMME |  |  | Code | Eric | DM/MD: Vinayak DM/MD: Brett DM/MD: Jose | SP 2: 5/9/2016-5/27/2016 SP 3: 5/30/2016-6/17-2016 SP 4: 6/20/2016-7/8/2016 |  | Rick Gilormo (rg1854) | Rick Gilormo (rg1854) | Ram Iyer (sr7489) | 5/9: Tony told Eric today that Jose is leaving. Brett will take over this project. Eric gathered the work scope and status from Jose today. Eric will clean up the US tasks to be more meaningful. 4/21: Eric just found this project today assigned to him via Tony's project assignment spreadsheet. No idea what is involved in this project.
1610 | 285867 | 452726 | Ericsson vMME Certification (NFV) | vMME |  |  | Code | Dana | Dev Lead: Wes DM/MD: Wes SUM: Cynthia KPI: Yeab DMD: Jerome |  |  | Lon Tanner (lt4902) | Lon Tanner (lt4902) | Ram Iyer (sr7489) | 10/24: Project deployed. 10/5: Project is scheduled and on track to be deployed 16.10. 5/17: Tony told Eric that Dana will be assigned to this project since it is part of mobility. See Q discussion below. Eric(9:35:03 AM): Hi Dana. Please see the Q discussion below. Eric(9:31:07 AM): Who is going to be assigned as the iPOR dev lead for the 1610 285867? It is the continuation project for Jose's 1607 285867B that was reassigned to me. Tony(9:32:41 AM): is that vMM? Eric(9:32:47 AM): vMME Tony(9:32:58 AM): it will probably be Dana (Mobility) Tony(9:33:14 AM): but will use a new resource (since some folks are not being renewed) Eric(9:33:56 AM): Ok. I'll let Dana know. Ram is starting his work on the 1610 USs 5/12: Rick emailed Eric the initial discussion on this project which will lead into the US reviews in a near future date. 5/12: Eric believes this project will be assigned to him ONLY because he it is related to the 285867B 1607 project that he took over from Jose Velasquez. Eric(10:54:36 AM): Hi Rick. Is 285867 1610 the continuation of 285867B 1607? Rick(10:56:20 AM): Hi. yes. for 1607, for vETL/Vertica we are loading all counters vertically. 1610 need to load all counters horizontally (last I heard) 4/21: Eric just found this project today in Tony's project assignment spreadsheet. It has NOT been assigned to an iPOR dev lead yet. | Cynthia: ST in progress
1610 | 285867 | 452726 | Ericsson vMME Certification (NFV) - PM data | vMME |  |  | Code | Mark | [6 empty] | 7/26: Tony assigned this project during the "Quick Discussion on Assignments" meeting
1607 | 286422A | 457044 | Nimbus 1.0 (vEPC) (Play 1) | VoIP |  | Nimbus | Cancelled | Eric | DMD: Alan/Yeab DM/MD: Srinivas DM/MD: Riya DM/MD: Binesh |  |  | Terri Marhoffer (tm3178) | Terri Marhoffer (tm3178) | Ram Iyer (sr7489) | 5/5: Eric got the dates from Terri and discovered that this is a large project with a very aggressive schedule. Eric & Terri were able to push the dev due dates out by 1 week. This is a mandate from Chee. There is no more room to adjust the dates. 5/5: Eric reviewed the QH doc and reviewed his comments with Ram & Srinivas. 5/3: Ram Iyer and Partha had the QH req review today. 4/28: Partha Kannaiyan sent meeting invite for 5/3 to review HLD. Ram Iyer sent the HLD over to Eric. 4/27: Terri informed Eric that this is a QH project. Ram should finish the QH doc by 5/2. 4/21: Eric just found this project today assigned to him via Tony's project assignment spreadsheet. No idea what is involved in this project.
1612 | 286422 | 454368 | Nimbus 1.0 (vEPC) (Play 1) | VoIP |  | Nimbus | Code | Eric | DMD: Alan/Yeab DM/MD: Srinivas (Ericsson) DM/MD: ?? (F5) DM/MD: Riya (CGWY DM/MD: Binesh (CGWY) |  |  | Terri Marhoffer (tm3178) | Terri Marhoffer (tm3178) | Ram Iyer (sr7489) Xinyu Huang (xh6263) | 7/20: Srinivas & Eric attended the HLD review session 7/19: Srinivas & Alan attnded the 1st HLD review session
1702 | 286422 | 454368 | Nimbus 1.0 (vEPC) (Play 1) | VoIP |  | Nimbus | Code | Eric | DMD: Alan/Yeab DM/MD: Srinivas (Ericsson) DM/MD: ?? (F5) DM/MD: Riya (CGWY DM/MD: Binesh (CGWY) |  |  | Terri Marhoffer (tm3178) | Terri Marhoffer (tm3178) | Ram Iyer (sr7489) Xinyu Huang (xh6263) | 5/10: Hung Ngo (hn1961) is trying to push his 1610 project to be a 1607 project but I told him that we don't have the bandwidth to do his NEW 1610 project in 1607. Hung has questions on how VETL needs the data files to be provided and Srinivas & Eric provided those answers. Hung also had question on DMD and Jerome & Yeab answered them. 4/21: Eric just found this project today assigned to him via Tony's project assignment spreadsheet. No idea what is involved in this project.
1702 | 286422B | 458815 | Nimbus 1 0 (vEPC) (Play 1) - Phase 2 | VoIP |  | Nimbus | Code | Eric | DMD: Alan/Yeab DM/MD: Srinivas (Ericsson) DM/MD: ?? (F5) DM/MD: Riya (CGWY DM/MD: Binesh (CGWY) | SP1 9/12/2016 - 9/30/2016 SP2 10/3/2016 - 10/ 21/2016 SP3 10/24/2016 - 11/11/2016 SP4 11/14/2016 - 12/02/2016 SP5 12/05/2016 - 12/23/2016 ETE 1/2/2017 - 1/13/2017 UAT 1/16/2017 -2/3/2017 Final Code Drop: 1/13/17 |  | Terri Marhoffer (tm3178) | Janet Perrineau (jp6581) | Ram Iyer (sr7489) Xinyu Huang (xh6263)
1704 | 286422B | 458815 | Nimbus | VoIP |  | Nimbus | Code | Eric | Srinivas |  |  | Janet Perrineau (jp6581) | Janet Perrineau (jp6581) | Ram Iyer (sr7489) | Fani requested to change NODE_TYPE NODETYPE in all CISCO Gateway table.
1710 1707 | QH-MS-170703 | 461126 | Nimbus 2.0 Quick Hit | VoIP |  | Nimbus | TSO | Eric | Alan (KPI Engine) | R06.4 3/20/2017 - 4/7/2017 R07.1 04/10/2017 - 04/28/2017 R07.2 05/01/2017 - 05/19/2017 R07.3 05/22/2017 - 06/09/2017 |  | Terri Marhoffer (tm3178) | Janet Perrineau (jp6581) | Fani Popovici | TSO, nothing to deploy | TSO, nothing to deploy
1712 1710 1707 | 294455 | 461126 | Nimbus 2.0 | VoIP |  | Nimbus | Code | Eric | Patricia (MD, KPI engine) Alan (KPI Engine) Kshama (DMD, DM, MD) Nag (KPI Engine, DM, MD) Patricia (KPI Engine, DM, MD) Riya (KPI Engine, DM, MD) Sachin (KPI Engine, DM, MD) | R06.4 3/20/2017 - 4/7/2017 R07.1 04/10/2017 - 04/28/2017 R07.2 05/01/2017 - 05/19/2017 R07.3 05/22/2017 - 06/09/2017 |  | Terri Marhoffer (tm3178) | Janet Perrineau (jp6581) | Ram Iyer (sr7489) Xinyu Huang (xh6263) | 2/16: Srinivas and Eric attended the TDP requirements review today | All DMs have been materialized and project is ready to deploy.
1712 1710 1707 | 294455 | 461126 | Nimbus 2.0 (GFP SAM) | VoIP |  | Nimbus | Code | Eric | Prasad (DMaaP) Kshama (DM, MD) Pradeep (DBA) Saran (ETL) Hector (Operations) | R06.4 3/20/2017 - 4/7/2017 R07.1 04/10/2017 - 04/28/2017 R07.2 05/01/2017 - 05/19/2017 R07.3 05/22/2017 - 06/09/2017 |  | Neelima Alluri (na912w) | Stephen Cardoza (SC662H) | Hung Ngo (hn1961) | 4/26: Janet & Hung say that this story needs to be done in the GFP SAM app under Nimbus since the work is not DCAE related. Should be charged to GFP SAM app with Stephen Cardoza (SC662H) as the scrum master and Neelima Alluri (na912w) as the PM. | All DMs have been materialized and project is ready to deploy.
1806 1802 | 299630 | 468131 | NIMBUS 3.0 Sprint 1 | VoIP |  | Nimbus | Code | Eric | Kshama Patricia Srinivas | IT1: R10.3 2/12/2018 – 3/09/2018 IT2: R11.1 3/12/2018 – 4/06/2018 IT3: R11.2 4/9/2018 - 5/04/2018 IT4: R11.3 5/7/2018 – 5/25 /2018 |  | Terri Marhoffer (tm3178) | Janet Perrineau (jp6581) | Ram Iyer (sr7489) | 1/30: Srinivas & Eric attended Ram's story review meeting 1/12: Janet confirmed that this project is now active. The story review should be around 1/31. Development should begin on 2/12. Janet did mention that this proiect will be aggressive with the schedule due to needing to align with the ECOMP schedule. 11/2: Janet confirmed that this project is still on hold and there is no ETA on when the hold will be lifted. 10/10: Terri sent email showing that this project is still on hold 9/5: Srinivas & Eric attended Ram's story review meeting today. Ram will create the stories in TDP later this week.
1707 | 294561 | 461244 | Neo 9.0/PCRF for Neo 9.0 (Part of Nimbus 2.0) | VoIP |  | Neo | Code | Eric Ravi | Zhenyuan (DM, MD) Nag (DM, MD) Prasad (DM, MD) | R06.4 3/20/2017 - 4/10/2017 R07.1 4/10/2017 - 5/1/2017 R07.2 5/1/2017 - 5/22/2017 R07.3 5/22/2017 - 6/12/2017 R07.4 6/12/2017 - 7/3/2017 OLD SP1 2/13 - 3/3 SP2 3/6 - 3/24 SP3 3/27 - 4/7 |  | Steven Rivenburg (sr807g) | Steven Rivenburg (sr807g) | Xinyu Huang (xh6263) | 5/10: This project was officially pushed to 1707 today 3/7: Ravi transitioned this project to Eric today | All DMs have been materialized and project is ready to deploy.
1710 | 296702 | 46608 | NEO ENTERPRISE 3.0 ( Capacity Augment and ADTM Release 4 support) | VoIP |  | Neo | Code | Eric | Sachin (DMaaP, DM, MD, KPI engine) | SP1 7/24/2017 -8/11/2017 SP2 8/14/2017 - 9/1/2017 SP3 9/4/2017 - 9/22/2017 SP3 9/25/2017 - 10/13/2017 |  | Yashika Johnson (yj838p) | Yashika Johnson (yj838p) | Xinyu Huang (xh6263) | 6/20: Xinyu held a story review today. 6/19: Xinyu Huang will hold a story review on 6/20 6/1: Eric asked Yashika via Q to add him into all related meetings. Yashika will provide a date for the story review meeting. They are still gathering requirements. 5/31: Dana informed Eric that this project should be assigned to him. Eric reassigned it to himself in iPOR | All DMs have been materialized and project is ready to deploy.
1711 | 300316 | 468266 | Neo 10 Sprint 1 | VoIP |  | Neo | Code | Eric | Manish (DM, MD, KPI engine) | Sprint schedule: 9/18 – 10/13 IST/ST: 10/16-11/2 E2E & UAT waived |  | Yashika Johnson (yj838p) | Yashika Johnson (yj838p) | Lichen Tan (lt540s) | 9/1: Eric sent email asking when the story review will take place. Lichen Tan (lt540s) responded that the story review meeting sould be on 9/7. Srinivas will have to attend this review meeting since Eric will be on vacation. 8/24: Toni informed Eric of this new NEO11 project. Eric sent Yashika an email saying that he will be the lead for all NEO projects. No ETA on story review meeting. | There is 1 DM (0315) that needs to still be materialized.
1712 | 300317 | 468679 | Neo 10 Sprint 2 | VoIP |  | Neo | Code | Eric | Patricia (DM, MD) | SP1: 10/16/2017 - 11/3/2017 SP2: 11/6/2017 - 11/24/2017 |  | Julius Sheppard (js009p) | Julius Sheppard (js009p) | Lichen Tan (lt540s) | 10/17: Julius held a grooming session today. Srinivas & Eric attended and committed to the work. Eric informed Patricia of this new work via Q. 10/11: Lichen Tan reviewed his HLD today. He will create the stories in TDP and let us know when done. 10/10: Lichen Tan scheduled a story review meeting for tomorrow. 10/3: Terri Marhoffer told Eric that the story reveiw meeitng will take place next week. This project will need to be delivered in 1712. All we know is that we need to add 1000+ counters. 9/27: Yashika responded saying that Julius Sheppard (js009p) will be the Scrum Master for this project. Julius says the AIS was needed by 9/22 and it's still not done. The project will probably get pushed to 18/01 9/22: Eric asked Yashika when stories will be reviewed 9/18: Terri informed Eric today about this new project. Lichen is still working on the HLD | All DMs have been materialized and project is ready to deploy.
1604 | 284862A / 284331 | 450165 | NetBond Expansion - Features and Footprint - Operational Requirements R2 | Netbond |  |  | Code | Huei | Huei | SP1 (284862a) 11/23-12/18 SP2 (284862a) 12/21-1/15/16 SP3 (284862a) 1/18-2/12/16 SP4 (284862a) 2/15-3/11/16 SP5 (284862a) 3/14-4/08/16 Release 4/16-4/17/16 |  | Allen Dee (ad118n) |  | Jeff Yu (xxxx) | Anthony(11:18:39 AM): i also got a Q today: Kurt(9:28:42 AM): FYI - Not sure if you are aware but 284862a for PMOSS_CUR/WUR that is targeted for 16.02 in the iPOR will be moved out to 16.04 as I was told... Anthony(11:18:51 AM): i have not seen anything on it but just a heads up
1607 | 284392 | 451410 | WPS NGN LTE/VoLTE Network |  |  |  | No impact | Ravi | [6 empty] | 4/21: Eric just found this project today assigned to Ravi via Tony's project assignment spreadsheet. Ravi will update all the required info on this project
1607 1610 | 289978 ECOMP 291047 | 456213 | Shared Platform ECOMP 163 Shared Platform ECOMP 164 | ?? |  |  | Code | Eric | DMD: Jerome or Yeab DM/MD: Eric | Due 6/13/2016 |  | Weili Wang (ww352v) | Weili Wang (ww352v) | Christen Corrado (cc584g) | 5/24: Eric met with Eric Noel, Yeab, Jerome & Alan to get clarity on what is needed in this project. This work is due in 1607 and NOT 1610. Below are the notes that Eric took during the meeting. • Eric Noel will work with PM to have respective USs created to account for this work in 1607. • Eric Noel will need to request to have a DMD contact added into this project in iPOR • Eric Gonzalez provided the Upstart QA an Prod KPI engine schema that Eric Noel will need to submit access to o PRIDE Vertica (QA) NVP KPI o Vertica (PROD) PRIDE NVP KPI • Yeab will send PDW_NVPKPI_VIEWS.VEPC_KPI table structure to Eric Noel • CLAMP (Eric Noel) will use data from Splunk, Nagios XL & Vertica for Eric Noel to crunch ~10 KPIs • A Unix system (no name today) will publish the KPI results to VETL via DMD (or DMaap if needed) • VETL will then load the KPI results into the PDW_NVPKPI_DB.VEPC_KPI table OR a brand new KPI result table if needed. | 9/28 Eric: This was deployed in 1607. Nothing to deploy in 1610
1609 | 290653 | ?? | NetBond Expansion - Nearest Exit Routing�Release 2 | Netbond |  |  |  | Ravi Sudhakar | DM/MD: Huei | [5 empty] | 6/7: Adam Beaver email Eric to attend the US reviews. Eric informed Adam that this project is assigned to Sudhakar and Huei. Eric forwarded invite to Sudhakar. 4/21: Eric just found this project today in Tony's project assignment spreadsheet. It has NOT been assigned to an iPOR dev lead yet.
1610 | 282055a | 456447 | [5 empty] | Brij | [6 empty] | 7/28: No VETL/Vertica impact per iPOR. 4/21: Eric just found this project today assigned to Brij via Tony's project assignment spreadsheet. Brij will update all the required info on this project
1610 | 282846 | [5 empty] | No impact | ?? | [6 empty] | 9/28: Eric checked this project in iPOR and noticed that it was cancelled 4/21: Eric just found this project today in Tony's project assignment spreadsheet. It has NOT been assigned to an iPOR dev lead yet. | 9/28 Eric: Checked this project in iPOR and noticed that it was cancelled
1610 | 286265 | 452554 | IP Flex Enhanced Features Server Scaling | vUSP |  |  | Code | Eric | Alan (DMD. KPI engine) Srinivas (DM, MD) Wes (MD) | IT1: 7/25/2016-8/5/2016 IT2: 8/8/2016-8/19/2016 |  | Jane Eisenmann (je3134) | Kris Hubble (wh4355) |  | 5/9: The USs that Ed has are mixed up and not written properly. Some of the USs assigned to VETL are really for either EA or WBG. Ed is going to clean up all the USs and redo the US review. As of the 6/9/2016 meeting, only US680709 was clear. 4/21: Eric just found this project today in Tony's project assignment spreadsheet. It has NOT been assigned to an iPOR dev lead yet. | 9/28 Eric: Project is ready for deployment
1702 | 287639 | [6 empty] | ?? | [6 empty] | 9/28: Eric checked iPOR today and noticed that this is now a 1702 project. No iPOR dev lead assignment has been made yet. 4/21: Eric just found this project today in Tony's project assignment spreadsheet. It has NOT been assigned to an iPOR dev lead yet.
1610 | 288001 | [6 empty] | ?? | [6 empty] | 9/28: Eric checked iPOR today and noticed project is NOT in iPOR 4/21: Eric just found this project today in Tony's project assignment spreadsheet. It has NOT been assigned to an iPOR dev lead yet. | 9/28 Eric: checked iPOR today and noticed project is NOT in iPOR
1610 | 288125 |  | 2016 SD&E TSA Standard Tools and Monitoring for D1/D2 |  |  |  |  | Ravi | [6 empty] | 9/28: iPOR shows this project assigned to Ravi 4/21: Eric just found this project today in Tony's project assignment spreadsheet. It has NOT been assigned to an iPOR dev lead yet. | 9/30 Ravi: TSO 9/28 Eric: Check with Ravi
1702 | 288584 | 457390 | VPMS Backend & DB | DCAE |  |  | Code | Brij | Jerome (Dmapp/DMD) Rajesh Meher (DM, MD) | IT1 – 7/25/2016 - 8/12/2016 IT2 – 8/15/2016 - 9/2/2016 IT3 – 9/15/2016 – 9/23/2016 |  | Terri Marhoffer (tm3178) | Janet Perrineau (jp6581) | Lichen Tan (lt540s) | 1/23: Comment from Brij – Our work has been completed. No further involvement needed from us (except during deployment). 9/2: Brij told Eric that he has bandwidth to take on another project. Eric gave Brij this project and informed Janet, SE and VETL/Vertica developers that Brij will manage this project going forward. 7/11: Eric attended the 2nd review session. No one attended the 1st review session. 4/27: Eric gathered all info available from iPOR 4/21: Eric just found this project today assigned to him via Tony's project assignment spreadsheet. No idea what is involved in this project.
1702 | 288584B | 459958 | VPMS Backend & DB | DCAE |  |  | Code | Brij | Jerome (Dmapp/DMD) Rajesh Meher (DM, MD) | IT1 – 7/25/2016 - 8/12/2016 IT2 – 8/15/2016 - 9/2/2016 IT3 – 9/15/2016 – 9/23/2016 |  | Terri Marhoffer (tm3178) | Janet Perrineau (jp6581) | Lichen Tan (lt540s) | 1/23: Comment from Brij – Our work has been completed. No further involvement needed from us (except during deployment). 9/2: Brij told Eric that he has bandwidth to take on another project. Eric gave Brij this project and informed Janet, SE and VETL/Vertica developers that Brij will manage this project going forward. 7/11: Eric attended the 2nd review session. No one attended the 1st review session. 4/27: Eric gathered all info available from iPOR 4/21: Eric just found this project today assigned to him via Tony's project assignment spreadsheet. No idea what is involved in this project.
1610 | 288779 | [6 empty] | ?? | [6 empty] | 9/28: Eric checked iPOR today and noticed project is NOT in iPOR 4/21: Eric just found this project today in Tony's project assignment spreadsheet. It has NOT been assigned to an iPOR dev lead yet. | 9/28 Eric: checked iPOR today and noticed project is NOT in iPOR
1610 | 288998 | [5 empty] | No impact | [7 empty] | 9/28: iPOR does not have any entry for VETL/Vertica so no impact 4/21: Eric just found this project today in Tony's project assignment spreadsheet. It has NOT been assigned to an iPOR dev lead yet. | 9/28 Eric: iPOR does not have any entry for VETL/Vertica so no impact
1610 | 289109 | 454848 | 10 - TDAR - 1892 - NET - Tech Care Project | PMOSS_Uverse |  |  | Code | Brij | Dev Lead: Wes DM/MD: Manish |  |  | Theresa Siordia-Rybarski (ts1916) | Theresa Siordia-Rybarski (ts1916) | Rick Quagliata (rq2591) | 7/28: Updated Status/developer names. 6/13: Eric noticed a meeting was scheduled for this project for today and fowarded the invite to Brij. 6/2: Tony assigned this project to Brij during his team meeting today. Brij is now aware of this project and Eric forwarded the US review meeting to him. 4/21: Eric just found this project today in Tony's project assignment spreadsheet. It has NOT been assigned to an iPOR dev lead yet. | Brij: ST in progress
1702 1612 1610 | 289540b | 455442 | LTE Data Core Services Infrastructure Development - Gemalto OTA Architecture (#184420) Mobility-LTE | Mobility |  |  | Code | Dana | Dev Lead: Srinivas DM/MD: Rajesh, Sameer |  |  | AGARWAL, SHASHANK <sa1413@att.com> | AGARWAL, SHASHANK <sa1413@att.com> | Justine Lau | 1/13/16: Lab remains unavailable but this project will move forward and deploy in the dark. 11/10: Need 2 weeks to perform DIT once the lab becomes available. 10/24: Project moved to 17.02 release due to lab availability. Prism ID changed to 289540b. 10/5: The lab remains unavailable for this project. No date has been provided for the expectant availability of the lab. Development that does not require data has been completed. This project will most likely be delayed until the 17.02 release. 4/21: Eric just found this project today in Tony's project assignment spreadsheet. It has NOT been assigned to an iPOR dev lead yet.
1610 | 289865 | 457984 | NexGen SeGW for AIC-Mobility Small Cell | Mobility |  |  | Code | Dana |  |  |  | AGARWAL, SHASHANK <sa1413@att.com> | AGARWAL, SHASHANK <sa1413@att.com> | PENG, JIYA | 11/14: Dana checked and project is still on hold. 9/28: Eric checked iPOR and this project is assigned to Dana and marked "On-Hold" 4/21: Eric just found this project today in Tony's project assignment spreadsheet. It has NOT been assigned to an iPOR dev lead yet. | 9/28 Eric: checked iPOR and this project is assigned to Dana and marked "On-Hold"
1712 | 282360 | [5 empty] | Cancelled | Eric | [6 empty] | 11/28: Cancelled. No longer in iPOR 7/26: Tony assigned this project during the "Quick Discussion on Assignments" meeting 4/21: Eric just found this project today in Tony's project assignment spreadsheet. It has NOT been assigned to an iPOR dev lead yet. | Project cancelled
1610 | 285940 | 452254 | UC-Video-ATS-Release-15.2 | UC |  |  | Code | Eric | Wes (DM, MD) | IT1: 7/13/2016-8/2/2016 IT2: 8/3/2016-8/23/2016 IT3: 8/24/2016-9/13/2016 |  | Jane Eisenmann (je3134) | Emily Montgomery (es9137) | Ming-Ming Yu (my2263) | 6/10: Eric and Wes attended a US review meeting hosted by Ming-Ming. The Uss are clear and this project is very small. The iterations will be discussed during a grooming session. Wes is aware of the existing tables since Mike Smith transitioned that work over to him. | 9/28 Eric: Project is ready for deployment
1610 | 283495 | 447840 | Burstable Ethernet |  |  |  |  | Sudhakar | ??Huei?? |  |  | Kurt Smith (ks7543) |  |  | 6/13: Eric asked Sudharkar if he is assigned to all CUR/WUR projects and he confirmed that he is. Eric forwarded invite to Sudhakar for a US review session today. | Cynthia: ST in progress
1607 1610 | No PID but will use 283554A | None | PCI Tool | All |  |  | Code | Sudhakar | Srinivas | IT 1: 6/22 – 7/12 |  | Lon Tanner (lt4902) | Lon Tanner (lt4902) | Ron Ebright (re6013) | 9/28: Sudhakar is managing this project. 6/15: Eric attended the 1st US review session but none of the Uss for VETL/Vertica were discussed. Limited notes were gathered. Eric will ask Tony who is going to be assigned to this project. Iteration 1: 6/22 – 7/12 SE: Ron Ebright Domains: All Only existing data from Vertica will be provided to Teradata Not clear: Rainstor will be used as a one-way feed into the green Teradata DB | 9/28 Eric: Check with Sudhakar as he is managing this project on his own.
1610 | 285890 | 456993 | D2.0 - Virtual IPBE Certification (Play 1) | VoIP |  |  | Code | Eric | Riya (DM, MD) Wes (DM, MD) training Manish Cynthia (KPI engine) Srinivas (Load) Alan (MD) | IT1: 7/13/2016-8/2/2016 IT2: 8/3/2016-8/23/2016 IT3: 8/24/2016-9/13/2016 |  | Jane Eisenmann (je3134) | Jane Eisenmann (je3134) | Ming-Ming Yu (my2263) | 7/11: This is a VOIP project dealing with CDR data so Eric believes it will be assigned to him. 6/21: Eric found this invite today that took place yesterday when he was on vacation. Eric asked Tony who is being assigned to this project. Waiting on response. | 9/26: Cynthia: KPI config done in Dev & ST 9/28 Eric: Project is ready for deployment
1610 | 290932 | 458551 | Acceleration of IP Interconnection | VoIP |  |  | Code | Eric | Cynthia (DM, MD) | N/A |  | Jane Eisenmann (je3134) |  | Cho Wong (A53E03) | 6/23: Cynthia & Johan attended the HLD review. PCC has performance issues with using SFTP & DMD to VETL so PCC may just continue sending this data to Teradata. If so, then the migration of the tables and loads from Teradata to Vertica may go on hold. Cho Wong will let us know by mid next week of the final plan & solution. 6/23: Eric forwarded HLD review to Cynthia due to conflicts. She will gather the notes/work for VETL/Vertica. 6/23: No response from Tony but Eric realized that this is a VOIP project so he assigned it to himself in iPOR. 6/21: Eric found this invite today for an HLD review for Thursday (6/23). Eric asked Tony who is being assigned to this project. Waiting on response. | 9/28 Eric: Project is ready for deployment
1610 | 289120 | 457688 | L0/L3 SDN - Multi-layer SDN Management of CBB on CRS and hiT7300 | VoIP |  |  | Code | Brij | Dev Lead: Srinivas Dmaap: Jerome DM/MD: Zhenyuan/Cynthia |  |  | Weili Wang (ww352v) | Amar Padmesh Gurajapu (ag753n) | Stephen Lam (sl679r) | 7/28: Jerome working on DMaap to VETL integration. 2 tables each with 25 fields. 6/22: Ravi mentioned this project in the chat room today. Ravi and Brij talked offline and determined that Brij should own this project. Ravi Yelesvarapu(11:14:10 AM): Hi All - who is handling 288733 Srinivas Krishnamurthy(11:14:35 AM): Brij Ravi Yelesvarapu(11:16:17 AM): Hi Brij - I was on a call related to 289210 and they are looking for commitment from us for it Ravi Yelesvarapu(11:16:22 AM): below is the summary of the project. Ravi Yelesvarapu(11:16:26 AM): 1610 - 289120 - 2 new feeds using existing interface as 288733 - Additional 5 GB of data per year approximately. Commitment needed by tomorrow. Follow on to 288733. | Cynthia: ST in progress
1702 | 289120a | ?? | Multi-layer SDN Management D2 0 R2 | VoIP |  |  | ?? | Brij |  |  |  |  | Steve Delgado | Stephen Lam (sl679r) | 1/23: Comment from Brij – This project is On Hold as per PRISM. 10/4: Srinivas said that Brij is working on this project. Eric confirmed with Brij. Eric updated iPOR and the All Projects.xls to show Brij assigned to this project. 9/14: Eric & Ravi asked Tony today who is assigned to this project? Eric is assigned to it because it is a D2 project for DCAE SDN (SW Defined Network)
1607 | 290744 | 456847 | AIC 3.0 Impact ? ECOMP 163 | VoIP |  |  | Code | Ravi - ry3304 | Ravi - ry3304 |  |  | Weili Wang (ww352v) | Weili Wang (ww352v) | Wen Shang (ws4361) | 6/22: Ravi mentioned that this project is assigned to him via his project call on 6/22 4/21: Several US are missing; SE to add and finalized - then we will review what is required. This possibly needs a VPMO for hardware. 4/18: Dana just found out this was assigned to her
1610 | 290330A | 457242 | ADIoD GA Blockers - Release 1610 | VoIP |  |  | Code | Ravi | Dev Lead: Ravi DM/MD: Ravi |  |  | Weili Wang (ww352v) | Weili Wang (ww352v) | Wen Shang (ws4361) | 6/23: Weili Q'd Eric and said that Ravi is assigned to this project. | 9/26: Ravi: Deployed with 1609
1612 | 291687 | 456749 | TRG LTE Optima Vertica Migration | VoIP |  |  | Code | Todd Placher | Wes |  |  | Not Assigned | Not Assigned | Michael Hoornstra
1610 | 290444 | 455927 | Sundance 2.2 | VoIP |  |  | Code | Dana | Dev Lead: Rajesh DM/MD: Zhenyuan (F5FWLB), Rajesh, Sameer |  |  | Terri Marhoffer (tm3178) | Terri Marhoffer (tm3178) | Justine Lau | 10/24: Project deployed. 7/28: Changes to F5FWLB - Zenyuan. | 9/27/2016 : ST is in progress.
1610 | 283866A | 457640 | IPX Hub for IP Interop - TD Network OSS - eCOMP MSO automation PM | VoIP |  |  | Code | Eric | Alan (KPI) Srinivas (DM/MD) Cynthia ( DM, DMD, MD) | IT1 7/13/2016-8/2/2016 IT2: 8/3/2016-8/23/2016 IT3: 8/24/2016-9/13/2016 |  | Jane Eisenmann (je3134) | Jane Eisenmann (je3134) | Didi Xie (dx080q) | 7/22: Srinivas, Alan & Eric attended the 2nd US review session. A 3rd review session will be held later today since Didi's laptop had issues. 7/20: Srinivas & Eric attended the 1st US review session | 9/26 Cynthia: ST in progress 9/28 Eric: Project is ready for deployment
1609 | 288416B |  |  | VoIP |  |  | TSO | Eric | [6 empty] | 7/26: Tony assigned this project during the "Quick Discussion on Assignments" meeting
1610 | 291014 |  |  | VoIP |  |  | No Impact | Eric | [6 empty] | 9/28: Eric checked iPOR today and noticed project is NOT in iPOR 7/26: Tony assigned this project during the "Quick Discussion on Assignments" meeting | 9/28 Eric: checked iPOR today and noticed project is NOT in iPOR
1610 | 291015 |  | Guided Design ECOMP 164 | VoIP |  |  | No Impact | Eric | [6 empty] | 9/28: iPOR does not have any entry for VETL/Vertica so no impact 7/26: Tony assigned this project during the "Quick Discussion on Assignments" meeting | 9/28 Eric: iPOR does not have any entry for VETL/Vertica so no impact
1610 | 290766 |  | vDNS Closed Loop Automation using vPRO Policies | VoIP |  |  | Code | Ravi Eric | [6 empty] | 7/26: Tony assigned this project during the "Quick Discussion on Assignments" meeting | 9/30: No 1610 VETL/Vertica impact 9/28 Eric: Get status from Ravi
1610 | 291046 |  | Hardware Ingest ECOMP 164 | VoIP |  |  | Code | Ravi Eric | [6 empty] | 7/27: Eric reassigned this project to Ravi today since Eric will be on vacation for the next 2 weeks and this project has NOT had any US review sessions. 7/26: Tony assigned this project during the "Quick Discussion on Assignments" meeting | 9/26: Ravi: Part of scope deployed with 1609. 5 A&AI Table changes deploying in 1610
1610 | 291047 |  | Shared Platform ECOMP 164 | VoIP |  |  | Code | Ravi Eric | [6 empty] | 7/27: Eric reassigned this project to Ravi today since Eric will be on vacation for the next 2 weeks and this project has NOT had any US review sessions. 7/26: Tony assigned this project during the "Quick Discussion on Assignments" meeting | 9/26: Ravi: No Impact
1610 | 291680 |  | AIC 3.5 Impact ECOMP 164 | VoIP |  |  | Code | Ravi Eric | [6 empty] | 7/27: Eric reassigned this project to Ravi today since Eric will be on vacation for the next 2 weeks and this project has NOT had any US review sessions. 7/26: Tony assigned this project during the "Quick Discussion on Assignments" meeting | 9/26: Ravi: No Impact
1610 | 290897a | 457776 | 290897a- AT T Split Project for SR 10 3 g Migration to UCS | VoIP |  |  | Code | Mark Ravi Eric | [6 empty] | 9/14: Tony told Eric to assign this project to Mark in iPOR and to forward the US review meetings to him. 7/28: Assigned to Mark, as only module impacted is PMCM. No VETL/Vertica impact. 7/27: Eric reassigned this project to Ravi today since Eric will be on vacation for the next 2 weeks and this project has NOT had any US review sessions. 7/26: Tony assigned this project during the "Quick Discussion on Assignments" meeting | 9/28 Eric: Get status from Mark
| 288290 |  |  | VoIP |  |  |  | Mark | [6 empty] | 7/26: Tony assigned this project during the "Quick Discussion on Assignments" meeting
| 289643 |  |  | VoIP |  |  |  | Mark | [6 empty] | 7/26: Tony assigned this project during the "Quick Discussion on Assignments" meeting
1604 | 284331 | 447315 | NextGen NBFW (Network Based and NetBond) | VoIP |  |  |  | Huei | Huei | SP1 (284331) 12/15-1/11 SP2 (284331) 1/12-2/8 SP3 (284331) 2/9-3/7 SP4 (284331) 3/8-4/4 SP5 (284331) 4/16-4/17 Release |  | Jane Chung (jc1858) | Jane Chung (jc1858) | Jeff Yu (xxxx) | Anthony(11:18:39 AM): i also got a Q today: Kurt(9:28:42 AM): FYI - Not sure if you are aware but 284862a for PMOSS_CUR/WUR that is targeted for 16.02 in the iPOR will be moved out to 16.04 as I was told... Anthony(11:18:51 AM): i have not seen anything on it but just a heads up | Brij: ST in progress
1610 | 289266 |  | SMART : Project Aegis | VoIP |  |  |  | Ravi | [6 empty] | 7/28: One table over new DMD topic in new Vertica Schema. EA/KPIs involved. | 09/26: Ravi: In ST. Code handed off couple of weeks back. Nothing outstanding from Dev at this time. On Track for 1610 Deploy.
1612 | 289266A | 460241 | Project Aegis PMOSS_INSIGHTS_Added_Scope | VoIP |  |  | Code | Ravi |  |  |  | Kris Hubble (wh4355) | Kris Hubble (wh4355) | Didi Xie (dx080q) | 11/29: Ravi : Drop 2 Tables and support EA/WBG KPIs. 10/24: Eric noticed that the 1610 289266 project was assigned to Ravi. Ravi stated that the new 1702 289266A should be assigned to him as well. Eric updated iPOR and informed Kris Hubble of the reassignment. 10/21: Tony asked Eric to find someone to assign this VOIP project to. I don't have the time to ask around so I assigned it to myself (Eric). | 11/29: Ravi : In ST. KPI testing progress. No DM impacts expected.
1610 | 290995 |  | AIC - vFW Development (GT4F.01) - 3Q (1610) | VoIP |  |  |  | Ravi | [7 empty] | 09/30: Ravi will update status.
1610 | 291726 |  | AIC Operations Engineering 1610 | VoIP |  |  |  | Ravi | [7 empty] | 09/26: Ravi: Deployed with 1609
1610 | 289744 | 456887 | USP1610 Critical Features | VoIP |  |  |  | Ravi | [6 empty] | 8/15: Eric checked iPOR to confirm it's still assigned to Ravi. Informed Kris Hubble that Ravi is the iPOR dev lead. | 09/26: Ravi: In ST. Code handed off couple of weeks back. Nothing outstanding from Dev at this time. On Track for 1610 Deploy.
1602 | QH-151004 (for doc puposes) but part of 283427-6 | 445690 | Compass to support Gamma vPE for D2.0 | VoIP |  |  | Code |  |  | Draft Schedule to be agreed by the team HLD: Done Design: due date- 12/4/2015 (3 ½ weeks) Development: completed by 1/8/2016 (5 weeks development) and HO to ST on 1/11/2016 ST: from 1/11 – 2/12/2016 (5 weeks testing) Code freeze: 2/15-2/19/2016 Deployment: 2/20/2016 |  | Weili Wang (ww352v) |  | Su-lin Jeff Yu (jy6277) |  | Brij: ST in progress
1702 | 289865 | 457984 | NexGen SeGW for AIC - Mobility Small Cell | VoIP |  |  | ??? | Dana |  |  |  |  | AGARWAL, SHASHANK <sa1413@att.com> | PENG, JIYA | 10/5: Project on-hold per iPor.
1702 | 291201 | 458555 | FOTA - Network Realization | VoIP |  |  | Code | Dana | Dev Lead: Rajesh |  |  | PERRINEAU, JANET |  | TONG, JASPER | 11/14: Notified by the PM that this project is being descope; no work is to occur on the project until further notice. 10/21: Review and approved AID.
1702 | 292844 | 459141 | Glacier - NDA Project | VoIP |  |  | Code | Dana | vETL EE: Rajesh |  |  | Terri Marhoffer (tm3178) |  | Chadi Diab | 11/14: Pending location of data in PMOSS OPTIMA; secure message sent to Mark Scott and Chadi Diab
1701 1612 | 292476 | 458741 | Nokia NetAct EMS for LTE | VoIP |  |  | Code | Dana | Dev Lead: Rajesh DM/MD: Rajesh, Sameer |  |  | Terri Marhoffer (tm3178) |  | LiChen Tan | 1/13/17: Ready for deployment.
1702 | 289745 | 457490 | IP Real Time Text (RTT) (Play 2) - BHS | VoIP |  |  | Code | Eric | Cynthia (DMaaP, DM, MD) Alan (KPI Engine) Wes (DM) | IT1: 09/19/2016 to 10/18/2016 IT2: 10/19/2016 to 11/18/2016 IT3: 11/19/2016 to 12/18/2016 |  | Subrahmanyam Jonnavittula (sj896b) | Subrahmanyam Jonnavittula (sj896b) | Cho Wong (cw1728) | 9/22: The PM informed Eric that Tony assigned this project to him. Eric attended the 1st US review session today. 8/30: Tony mentioned this project in the below Q discussion. Tony(9:45:44 AM): Hey, is Abhishak working on any of your items? Tony(9:45:49 AM): i just got a request: Subrahmanyam(7:47:42 AM): Hi Anthony, GM! This is Subra from PMOSS-VoIP. I have one quick question. Can I request Abhishek Bagarka for DCAE-PRIDE Module Requirement Overview session conducting by SE for the proejct 289745? Eric(9:48:47 AM): I don't have Abhishak assigned to any of my projects Tony(9:49:01 AM): ok Eric(9:49:51 AM): Who is assigned to that 289745 project? Eric(9:49:59 AM): I'll go check iPOR Eric(9:51:16 AM): iPOR has no assignment for that 1702 project
1610 | 290622a | 457938 | ASEoPON ICP Infrastructure Build - 1610 | VoIP |  |  | TSO | Ravi | [6 empty] | 9/6: This project is assigned to Ravi in iPOR. | 09/30 Ravi: TSO
1702 | 290708a | 458345 | Europe vEPC Expansion - EXP Only | VoIP |  |  | Code | Eric | Yeab (DMD/DMaaP) Alan (KPI engine) Bhanu (DM, MD Sachin (DM, MD) Prasad (DM, MD) Wes (DM, MD) | IT1: 10/3/2016 - 10/24/2016 dev due 10/17 IT2: 10/24/2016 - 11/11/2016 dev due 11/4 IT3: 11/14/2016 - 12/05/2016 dev due 11/28 |  | Yashika Johnson (yj838p) Janet Perrineau (jp6581) | Yashika Johnson (yj838p) Janet Perrineau (jp6581) | Rakhee Nair (rn146w) | 9/16: Eric received a US review session for this today. iPOR shows Eric assigned to this project
1702 | 293778 | 461190 | IP Interoperability - Per-Carrier Management of Routing and Protocols | VoIP |  |  | Code | Eric | Wes (DM, MD) | R05.3: 10/26/2016 - 11/15/2016 R06.1: 11/16/2016 - 12/6/2016 R06.2: 12/7/2016 - 12/27/2016 |  | Emily Montgomery (es9137) Subrahmanyam Jonnavittula (sj896b) | Emily Montgomery (es9137) Subrahmanyam Jonnavittula (sj896b) | Saxena Deepa (ds521a) June Shi (ys1362) | 10/26: Saxena Deepa held a US review session today & Wes and Eric attended. This project seems to be CDR related. 9/13: June Shi (ys1362) contact Eric via Q asking for a VETL/Vertica lead for this project. Since she said that this project is for USP in VOIP domain then Eric told her that he'll be assigned to it. This project is NOT in iPOR yet.
1610 | QH-MS-161005 | 455927 | Sundance 2.2 | Mobility |  |  | Code | Dana | Dev Lead: Rajesh DM/MD: Zhenyuan (F5FWLB), Rajesh, Sameer |  |  | Terri Marhoffer (tm3178) | Terri Marhoffer (tm3178) | Justine Lau | 10/24: Project deployed. | 9/27/2016 : ST is in progress.
1702 | 283912E | 458683 | SAREA Rel2e | PMOSS_COMPASS |  |  | Code | Brij | Vinayak (DMD, DM, MD) |  |  | Jane Chung | Jane Chung | Alan Gale | 1/23: Comment from Brij – User stories have been reviewed and approved by Brij/Vinayak. Vinayak will start working on this shortly. Ravi will be taking over this project when Brij transitions out of the team on 2/28. 9/28: Brij attended the first review call on (9/28) and found out the high-level scope.
1702 | 290916 | 459370 | ANIRA Gateway Upgrade for Hybrid VPN | VoIP |  |  | Code | Eric | Manish (DMaaP/DMD, DM, MD) Riya (DMaaP/DMD, DM, MD) Bhanu (DMaaP/DMD, DM, MD) Yeab (mentor) | IT1: 10/26/2016 - 11/15/2016 IT2: 11/16/2016 – 12/6/2016 IT3: 12/7/2016 – 12/27/2016 IT4: 12/28/2016 – 1/17/2017/2016 |  | Steve Delgado (sd1569) | Steve Delgado (sd1569) | Shau-Ann Chang | 10/3: Eric & Srinivas attended the 1st US review session today. Did not get to the VETL/Vertica Uss. No ETA on when the next US review session will take place. 10/3: Eric received a US review meeting and iPOR shows this project assigned to him.
1707 | 288487A | 458269 | Deconstructed Metro ROADM Release 2 | DCAE |  |  | Code | Ravi Brij | Jerome Arvidsson |  |  | Weili Wang (ww352v) | PERVINE, ERIN K (ed2178) | Charles Pittman | 1/23: This was originally Brij's project but has been transitioned to Ravi Yelesvarapu.
1612 | 289109 | 454848 | 10 - TDAR - 1892 - NET - Tech Care Project | PMOSS_Uverse |  |  | Code | Brij | Dev Lead: Wes DM/MD: Manish |  |  | Theresa Siordia-Rybarski (ts1916) | Theresa Siordia-Rybarski (ts1916) | Rick Quagliata (rq2591) |  | 11/29: Ready to deploy. No outstanding items.
1702 | 290313 | 458488 | NEO 8.0 | VoIP |  |  | Code | Dana | Dev Lead: Rajesh DM/MD: Rajesh | IT1: 11/21/2016 - 12/9/2016 IT2: 12/12/2016 - 12/30/2016 IT3: 1/2/2017 - 1/20/2017 |  | Yashika Johnson (yj838p) | Yashika Johnson (yj838p) | HUANG, XINYU ​ | 12/28: Continuing to work on additional 2 tables in requirement. Additional discussion required with Dana. 10/14: Tony told Eric to assign this project to Dana via Q.
1702 | 276959k | 459965 | ADTM OSS Support Work for MCS 2 2 | Mobility |  |  | Code | Toni | Dev Lead: Rajesh DM/MD: Rajesh |  |  | Steve Rivenburg | Steve Rivenburg | Justine Lau | 1/13/17: STO HO complete 12/28: Email sent to Justine/Chris. DEVKEY in all Neo enterprises table , SYS_DIAMETER table, we don’t have any column where we could load this field diamAgentHostCntSdTsrMsgs 11/10: Design assessment available 10/24: Meeting to approve the DDE's.
1702 | 292194 | 458956 | Nokia FSM4 | Mobility |  |  | Code | Toni | Dev Lead: Rajesh DM/MD: Rajesh |  |  | Steve Rivenburg | Steve Rivenburg | Kannayain Parthasurathy
1702 | 293477 | 459884 | Sundance 2.2.5 | Mobility |  |  | Code | Dana | Dev Lead: Rajesh DM/MD: Rajesh |  |  | Steve Rivenburg | Steve Rivenburg | Justine Lau | 1/13/17: Dev complete. ST HO to be scheduled. 12/29: Tables complete. Working metadata. 11/10: Design assessment available. 10/18: DDE Review/Approval
1702 | 293653 | 461529 461307 | Ops Engineering ECOMP 171 | VoIP |  |  | Code | Eric | Sachin (DM, MD) |  |  | Swati Chauhan (ss3064 | Swati Chauhan (ss3064 | Shau-Ann Chang
1704 | 296346 | 464666 | SDN-L Contrail | D2 ECOMP CONTRAIL |  |  | Code | Eric | Sachin Ransur |  |  | CHAUHAN, SWATI |  | SHANG, WEN | 17.02 Post Production Changes for increasing length of the below 3 tables was done CONTRAIL_ERROR CONTRAIL_BGP_PEER CONTRAIL_NETWORK_ROUTING_INST Post-MD Script to update the intfc_vrsn_cnter_grp_fld_mp table needs to be implemented for these tables
1707 | 296346 | 464666 | TechOps Contrail Theme 3 Package 1 | VoIP |  |  | Code | Eric | Sachin Ransur (DM, MD) | IT 37.1/SP 1 01/16/2017 - 01/27/2017 IT 37.1/SP 2 01/30/2017 - 02/10/2017 IT 38/SP 3 02/13/2017 - 02/24/2017 IT 38/SP 4 02/27/2017 - 03/10/2017 IT 39/SP 5 03/13/2017 - 03/24/2017 IT 39/SP 6 03/27/2017 - 04/07/2017 IT 40/SP 7 04/10/2017 - 04/21/2017 IT 40/SP 8 04/24/2017 - 05/05/2017 |  | Weili Wang (ww352v) | Swati Chauhan (ss3064) | Wen Shang (ws4361) | 2/20: EPIC review meeting will take place on 2/21 2/16: Ken Stone will have file layouts ready in SP4 and we would do our work in SP5-6. These are 2 week sprints and I said that we need about 3 weeks to create the objects and do DIT and then get to ST HO. USs will be written by end of next week by Ken Stone. 2/16: Swati sent email with the IT schedule for this upcoming project. No ETA on when the US review meeting will be held. | There is 1 DM (0166) that needs to still be materialized.
1702 | 286265A | 459407 | IP Flex Enhanced Features Server Scaling R1 | VoIP |  |  | Code | Eric | Senthil (DM, MD) |  |  | Kris Hubble | Kris Hubble (wh4355) | Ed Berberich (eb1847) | 11/16: Ed Berberich had a meeting to go over the VETL/Vertica work that is needed. The US does NOT exist today and will be created only if the client still wants to move foward with this work in 1702. Kris Hubble will inform us of the decision 11/15: Tony stated that this project will need to move to 1704 via email sent today. 11/11: Eric found this project in iPOR assigned to him but no info on this project has been provided yet. No meeting have started. Eric sent Q to Kris Hubble below. Eric(10:25:38 AM): Hi Kris. Can you provide me a status on the project below? I believe this project will come my way but I have 0 info on it. 286265a IP Flex Enhanced Features Server Scaling R1 WKH(10:28:32 AM): Eric, epics are still being worked so the project is way behind. Since it is on the eCOMP committed list for 17.02, we may be forced to do it whatever the case. It will be very similar to 286265 for 16.10. forwarded the epics to you via email. Ed will start on the user stories when he returns on Monday.
1702 | 285890A | 457335 | Develop vIPBE for Domestic BVoIP Services - IPTF | VoIP |  |  | Code | Eric | Riya (DM, MD) |  |  | Emily Mongomery | Emily Mongomery | Ming-Ming Yu (my2263) | 10/25: Chadra Mohan Raju informed Srinivas and Eric about this 1702 project.
1702 | 289278 | 456898 | 1- DNS Resolver & NTP Migration (Uverse/MIS) to AIC target Architecture | PMOSS COMPASS |  |  | Code | Brij | Vinayak |  |  |  | Steve Delgado (sd1569) | Richard Quagliata (rq2591) | 1/23: Comment from Brij – User stories have been reviewed and approved by Brij/Vinayak. Vinayak completed some of the work but some new user stories have been added which Vinayak is currently working on. 11/15: Tony asked Eric to assign this project to Dana. Eric(7:55:47 AM): GM. Can you please let me know who will be assigned to the project below? 1702 289278 "1- DNS Resolver & NTP Migration (Uverse/MIS) to AIC target Architecture" Tony(7:56:44 AM): Dana is taking that one Eric(7:57:02 AM): Ok. Want me to add her name in iPOR? Eric(7:57:08 AM): I'm there now Tony(7:57:11 AM): we might hand it back off to brij when he is back from PTO, but we will play that by ear, for now its Dana Tony(7:57:13 AM): sure please
1704 | 289278 | 456898 | 1- DNS Resolver & NTP Migration (Uverse/MIS) to AIC target Architecture | PMOSS COMPASS |  |  | Code | Eric Brij | Vinayak |  |  |  | Steve Delgado (sd1569) | Rich+R168:W168ard Quagliata (rq2591) | 4/5: Need to update a production table
1707 | 290536 290536A | 459706 220153 | Virtual FlowLogic probe | VoIP |  |  | Code | Eric | Prasad (DMaaP, MD, KPI engine) | IT4 3/27/2017 - 4/14/2017 IT5 4/17/2017 - 5/5/2017 IT6 5/8/2017 - 5/26/2017 OLD IT4 3/20/2017-4/8/2017 IT5 4/10/2017-4/28/2017 IT6 5/1/2017-5/20/2017 |  | Yashika Johnson (yj838p) | Yashika Johnson (yj838p) | Payal Mutha (pm144w) | 2/7: Eric cannot find 290536A in iPOR. Payal will ask Yashika to correct the 1707 290536 project and add the "A" to it as in 290536A. 1/23: Tony asked Eric to attend the "17.07 Package 1 Features" meeting hosted by Bob Ferro. Below are the notes that Eric was able to capture from this very high level meeting. PID 290536 • PMT 220153 • Vertica: Will load data • Initiative Name: vFlowLogic • Feature Description: o Provide existing capability to be configured to collect all fault and performance events, from the host OS, the guest OS and the application. Faults will be captured in one of two ways: o The faults will be SNMP and PM events will be file copy o The faults and PM events will be AT&T VES standard (future requirement) 11/15: Eric found this project in Tony's project commitment email sent out today. | All DMs have been materialized and project is ready to deploy.
1612 | 289744CO | 456887 | USP1610 Critical Features - Left over work | VoIP |  |  | Code | Ravi | [6 empty] | 11/29: Ravi: Project involves canges to 1 table (drop 1 column). Adding 1 new counter group. | 11/29: Ravi: In ST. Ready to Deploy. No outstanding items.
1702/1612 | 289544 | 459116 | NetBond Advanced Reporting | VoIP |  |  |  | Ravi/Huei |  |  |  | Kurt Smith |  | Kushal Jain/Ed Gujju | 11/29: 1702 project, but some performance improvement related changes are planned to be deployed with 1612. | 11/29: Ravi: Data model changes are in ST for 1612 related changes.
1707 | 290573 | 460018 | D2 - HSS Virtualization | VoIP |  |  |  | Dana | Dev Lead: Rajesh DM/MD: Rajesh |  |  | Yashika Johnson (yj838p) |  | Ram Iyer | 6/20: ST HO complete.
1708 | 290573 | 461126 | D2 - HSS Virtualization (Ref# 231912) | VoIP |  |  |  | Toni / Eric | Patricia (DM, MD, KPI engine) Alan (KPI engine) Srinivas (DM) Gourav (MD) |  |  | Yashika Johnson (yj838p) | Yashika Johnson (yj838p) | Ram Iyer | 7/22: It was decided to deploy 1712 Nimbus 294455 KPI engine work in 1708 release. | All DMs have been materialized and project is ready to deploy. There is still DIT needed for F5 data by Gourav but that should be completed before deployment.
1707 | 296156 | 205917 | T07 7 2c - TechOps ECOMP Theme 7 Package 2 | ? |  |  | TSO | Eric | NA | [5 empty] | 6/28: According to iPOR this project is TSO so nothing to deploy in 1707 1/23: Tony asked Eric to attend the "17.07 Package 1 Features" meeting hosted by Bob Ferro. Below are the notes that Eric was able to capture from this very high level meeting. PID 296156 • PMT 205917 • Vertica: Will enrich alarms on Vertica • Initiative Name: Tech Ops • Feature Description: o For 1707, VNF type standard names must be enforced. Impacts: VID, MSO, controllers? Assume: ASDC is not impacted | TSO, nothing to deploy
1707 | 296115 | 463890 | 7.2 (8) Design Platform Enh ECOMP 173 | VoIP |  |  | Code | Eric | Jerome (DMaaP) Wes (DM, MD) | IT 37.1/SP 1 01/16/2017 - 01/27/2017 IT 37.1/SP 2 01/30/2017 - 02/10/2017 IT 39/SP 3 02/13/2017 - 02/24/2017 IT 39/SP 4 02/27/2017 - 03/10/2017 IT 40/SP 5 03/13/2017 - 03/24/2017 IT 40/SP 6 03/27/2017 - 04/07/2017 IT 41/SP 7 04/10/2017 - 04/21/2017 IT 41/SP 8 04/24/2017 - 05/05/2017 | Sachin Sahai (ss669t) | Weili Wang (ww352v) | Weili Wang (ww352v) | Shu-Ann Chang | 1/23: Tony asked Eric to attend the "17.07 Package 1 Features" meeting hosted by Bob Ferro. Below are the notes that Eric was able to capture from this very high level meeting. PID 296115 • PMT 203963 • Vertica: Will load data • Initiative Name: ECOMP • Feature Description: o ECOMP component alignment with model changes (Tech Ops #F32219) o ECOMP Parameter standardization for operations (e.g. NF-type and NFC-Type) o Standard list of NF-Type (Created during Onboarding, Dictionary, Governance, Agreement across all ECOMP and Ops); NFC-Type will vary by vendor and can't be a dictionary item. o Attribute changes (Bennett governance) o Add new fields to inventory (SDN-C, App-C,A&AI) o Add new fields to enriched data feeds and store in Data Lakes (DCAE) o Note: CCD may also be impacted | All DMs have been materialized and project is ready to deploy.
1704 | 291662 | 458820 | 32.1b - Telecom Spend SI 37106 - 32.1b | VoIP |  |  | Code | Eric Brij | Kshama Punj |  | Marek Ruszala | Shashank Agarwal (sa1413) | Shashank Agarwal (sa1413) | Shu-Ann Chang | 1/23: Comments from Brij – Kshama is still waiting for Rowena (PEC) and the SE (Shau-Ann Chang) to provide finalized file layouts, so that she can begin her DM work.
1704 | 283912E | 458683 | SAREA Rel2e | VoIP |  |  | Code | Ravi Brij | Vinayak (DMD, DM, MD) |  |  | Jane Chung | Jane Chung | Alan Gale | 1/23: Comment by Brij - Ravi will be taking over this project when Brij transitions out of the team on 2/28. There is a 1702 project with the same exact Project ID. This is basically just the continuation of that previous 1702 project. As per the scrum master/PM (Jane Chung) -- Jane(4:12:18 PM): In PRISM, it’s the same PID. But for iPOR, I indicated 2 different releases by naming 17.02 as 283912e & 17.04 as 283912e-co.
1704 | 292577 | 460228 | ASTRA-Network Management Support for CSO | VoIP |  |  |  | Eric Brij | Kshama Punj |  | MEENAKSHI GOYAL | Jane Chung | Jane Chung | Stephen Lam | 1/23: Comment from Brij – Kshama has completed the work and will be making the ST HO shortly.
1705 | 292577-CO | 460228 | ASTRA-Network Management Support for CSO | VoIP |  |  | TSO | Eric | Kshama Punj |  | MEENAKSHI GOYAL | Jane Chung | Jane Chung | Stephen Lam | 4/26: Jane Chang asked who is the dev lead for this project. Kshama responed back saying it's Eric since it's a TSO project and a continuation of 292577 1704.
1702 | 290808A | 457775 |  | VoIP |  |  | Code | Brij | Mark Hoffman | [5 empty] | 1/23: Comments from Brij – Mark has completed the work for this and ST HO has been done. Minimal involvement from our side except attending weekly status call.
1707 | 296120 | 463868 | 11.1 (12) Migrate to open DCAE ECOMP 173 | VoIP |  |  | Code | Eric | Wes (DM, MD, KPI engine) Alan (DMaaP, DM, MD, SQL) | IT 37.1/SP 1 01/16/2017 - 01/27/2017 IT 37.1/SP 2 01/30/2017 - 02/10/2017 IT 38/SP 3 02/13/2017 - 02/24/2017 IT 38/SP 4 02/27/2017 - 03/10/2017 IT 39/SP 5 03/13/2017 - 03/24/2017 IT 39/SP 6 03/27/2017 - 04/07/2017 IT 40/SP 7 04/10/2017 - 04/21/2017 IT 40/SP 8 04/24/2017 - 05/05/2017 | SARAH MILLIGAN | Weili Wang (ww352v) | Swati Chauhan (ss3064) | Wen Shang (ws4361) | 2/23: Wes attended the US review meeting for Eric due to DR failover meeting conflicts. 2/20: Eric checked for any emails or meetings on this project but only an email about this future project from Christen Calhoun exists. 2/16: Weili asked who is the lead for this project. Tony assigned it to me. | All DMs have been materialized and project is ready to deploy.
1802 | 296120B | 466585 | T11 11_1b (12) Migrate to open DCAE ECOMP Carryover to 1802 | VoIP |  |  | Code | Eric | Patricia (DM, MD) Kshama (DM, MD, DMaaP) Jerome (JSON) | Amar provided these dates Sprint 1: 9/25/17 - 10/6/17 Sprint 2: 10/9/17 - 10/20/17 Sprint 3: 10/23/17 - 11/3/17 Sprint 4: 11/6/17 - 11/17/17 Swati provided the below IT 47 9/25/2017 - 10/16/2017 IT 48 10/17/2017 - 11/17/2017 |  | Amar Gurajapu (ag753n) | Amar Gurajapu (ag753n) | Minsky Luo (ml106g) | 9/1: Minsky stated that VETL/Vertica is TO in this story/project. The topics are still TBD. 8/24: Wes and Eric attended the continuation story review meeting. No stories were reviewed but Minsky said that VETL/Vertica would be code impacted for a NEW CDR topic subscription. 8/21: Wes & Srinivas attended the story review. Srinivas sent Eric a snapshot via Q showing that we're TO | All DMs have been materialized and project is ready to deploy
1707 | 293494 | 462981 | Deconstructed ROADM / Metro DWDM (L0/1) (Play 1) |  |  |  |  | Toni |  |  |  | Sasha NG (sn061h) | Sasha NG (sn061h) | Charles Pittman (cp8131) | 6/16: vETL/Vertica complete. API development still remains. 2/20: Eric checked iPOR today and noticed that this project is assigned to both Ravi & Eric 2/16: Weili asked who is the lead for this project. Tony assigned it to me.
1707 | 291662B | 459847 | 32 1b - Telecom Spend | DTV |  |  | Code | Toni Eric Brij |  |  |  | Shasank Agarwal (sa1413) | Shasank Agarwal (sa1413) | Shau-ann Chang (sc790u) | 6/5: ST HO complete. 2/27: This project was reassigned to Toni Q since it's DTV. Eric informed Shashan and Toni about the lead change. 2/17: Kshama sent invite to me at the time this EPIC review meeting started. Shasank Agarwal is the PM. TDP storeis are at https://sdp.web.att.com/fa5ccm1/web/projects/Performance_Quality_Management_LM_20.14.02#action=com.ibm.team.workitem.runSavedQuery&id=_8otl0PR9EeaSo94C0M4TBw
1707 | 292577A | 462030 | ASTRA-Network Management Support for CSO Rel 2A | ASTRA |  |  | Code | Dana Eric | Kshama Punj |  |  | Jane Chung | Jane Chung | Stephen Lam | 2/22: Jane Chung mentioned this project is coming. Asked if Kshama will be the developer and Eric stated that she possibly will but that can change. Since this project is ASTRA and not DTV or UVERSE then Eric will keep this project and not reassign it to Toni Q.
1710 1707 | 293864 | 461193 | Store & Forward - Virtualized Message Store (Component) | ?? |  |  | On hold | Eric | Patricia (DMaaP, KPI engine) |  | IBIS ROMAN | Terri Marhoffer (tm3178) | Terri Marhoffer (tm3178) | Jiya Peng (jp9990) | 5/23: Patricia asked if this project is still on hold. Jiya and Terri Marhoffer stated that the project is still on hold until further notice. 4/18: Per Jiya Pen project is currently put on-hold. 2/24: Srinivas & Eric attended the 2nd US review call today. This US was just added today and Eric will need to get the US req out of the HLD. 2/23: Eric & Srinivas attended Jiya Peng's (jp9990) HLD review meeting today. The call will continue tomorrow | Project is on hold
1707 | 296118 | 464060 | 9.5 (17) Telemetry Data Gen ECOMP 173 |  |  |  | Code | Eric |  | IT 37.1/SP 1 01/16/2017 - 01/27/2017 IT 37.1/SP 2 01/30/2017 - 02/10/2017 IT 33/SP 3 02/13/2017 - 02/24/2017 IT 39/SP 4 02/27/2017 - 03/10/2017 IT 40/SP 5 03/13/2017 - 03/24/2017 IT 40/SP 6 03/27/2017 - 04/07/2017 IT 41/SP 7 04/10/2017 - 04/21/2017 IT 41/SP 8 04/24/2017 - 05/05/2017 | Sachin Sahai (ss669t) | Weili Wang (ww352v) | Weili Wang (ww352v) | Minsky Luo (ml106g) | 3/3: Eric attended Minsky's US review meeting | All DMs have been materialized and project is ready to deploy.
1707 | 293640 | 461246 | D2 SIAD & Support for 10Gb/S Line-rate | MOBILITY |  |  |  | Dana | Dev Lead: Rajesh DM/MD: Rajesh |  |  | Shashank Agarwal |  | Xinyu | 6/9: ST HO complete.
1704 | 292194a | 461768 | Nokia FSM4 - LTE RTB Scorecard | Mobility |  |  | Code | Toni | Dev Lead: Rajesh DM/MD: Rajesh |  |  | Steven Rivenburg (sr807g) | Steven Rivenburg (sr807g) | LiChen Tang
1705 | 295256 | 462223 | OSS Ericsson ENM17A (EBS-L/KCI) | MOBILITY |  |  |  | Dana | Dev Lead: Rajesh DM/MD: Rajesh |  |  | Terri Marhoffer |  | LiChen Tang
1704 | QH-MS-170403 |  | Sundance QH | Mobility |  |  | Code | Dana | Dev Lead: Rajesh DM/MD: Rajesh |  |  | Terri Marhoffer |  | Justine Lau
1707 | 295782 | 464061 | Ericsson MME 2H 2016 Software Upgrades | MOBILITY |  |  |  | Dana | Dev Lead: Rajesh DM/MD: Rajesh |  |  | Terri Marhoffer |  | PARTHASARATHY, KANNAIYAN | 6/21: ST HO complete.
1707 | 288584c | 462853 | 1707 VPMS Backend DB | DCAE |  |  |  | Toni | Dev Lead: Rajesh DM/MD: Rajesh |  |  | PERRINEAU, JANET |  | MAREDDY, SURYAPRAKASH | 4/14: ST HO complete.
1709 | 297102 | 465580 | Nokia NetAct 17.2 P8 (Delta)- PMATT # 237282 | MOBILITY |  |  |  | Toni | Dev Lead: Rajesh DM/MD: Rajesh |  |  | Steven Rivenburg (sr807g) |  | PARTHASARATHY, KANNAIYAN
1709 | 297108 | 465579 | Nokia FSM4 Delta - PMATT # 237117 (w/DN Mapping Removal) | MOBILITY |  |  |  | Toni | Dev Lead: Rajesh DM/MD: Rajesh, Surendar |  |  | Steven Rivenburg (sr807g) |  | PARTHASARATHY, KANNAIYAN
1707 | 295752 | 463927 | MME WM 10.1 via SAM EMS | MOBILITY |  |  |  | Toni or Dana | Dev Lead: Rajesh DM/MD: Rajesh |  |  | Steven Rivenburg (sr807g) |  | Jasper Tong
1707 | 294923 | 464135 | Lightspeed HSIA 100G Connectivity to the CBB | UVERSE |  |  |  | Toni | Dev Lead: Rajesh DM/MD: Rajesh | [5 empty] | 6/26: It was determined there was no impact to vETL/Vertica.
1707 | 294454 | 464335 | Sundance 2.3 | MOBILITY |  |  |  | Dana | Dev Lead: Rajesh DM/MD: Rajesh |  |  | Steven Rivenburg (sr807g) |  | Justine Lau | 6/6: ST HO complete.
1707 | 296122 | 465100 | vMMSC AIC3.0 | MOBILITY |  |  |  | Dana | Dev Lead: Rajesh DM/MD: Rajesh |  |  | Terri Marhoffer |  | Justine Lau | 5/19: ST HO complete.
1709 | 297220 | 464265 | Cisco Small Cell 6.1 IT Release | MOBILITY |  |  |  | Toni | Dev Lead: Rajesh DM/MD: Rajesh |  |  | Terri Marhoffer |  | Michael Hoornstra
1707 | 285890C | 462938 | Develop vIPBE for Domestic BVoIP Services - Fault and Performance | VoIP |  |  | Code | Eric | Gourav (DM, MD, KPI engine) | IT1 = R07.1 2017-05-23 Std W 3w (4/12/2017-5/3/2017) IT2 = R07.2 2017-05-23 Std W 3w (5/3/2017-5/24/2017) |  | Emily Montgomery (es9137) | Emily Montgomery (es9137) | Ming-Ming Yu (my2263) | 3/17: Riya attended the US review meeting today. Eric had 2 other US review calls at the same time. 3/16: US review meeting was sent today and will take place tomorrow 3/15: Tony assigned this project to Eric in his iPOR spreadsheet. | All DMs have been materialized and project is ready to deploy.
1707 | 296084 | 462830 | Mobilization of AT&T Collaborate (TTM Release 2:1707) | VoIP |  |  | Code | Eric | Vinayak (DM, MD) Wes (DMaaP, DM, MD, KPI engine, export engine) Alan (KPI engine) | R06.4 3/22/2017 - 4/11/2017 R07.1 4/12/2017 - 5/2/2017 R07.2 5/3/2017 - 5/23/2017 |  | Jane Eisenmann (je3134) | Jane Eisenmann (je3134) | Yusef Bisrat (YB4820) | 3/27: Eric attended the US review session. Wes had to attend a meeting with Sekhar to discuss a CTI change 3/17: Wes & Eric attended June Shi's EPIC review meeting today. Eric could only attend the 1st 30 mins but Wes is going to take notes. Jane Eisenman is the PM. 3/15: Tony assigned this project to Eric in his iPOR spreadsheet. | All DMs have been materialized and project is ready to deploy.
1704 | 292194 | 458956 | Nokia FSM4 | Mobility |  |  | Code | Dana | Dev Lead: Rajesh DM/MD: Rajesh
1704 | 284331h | 458542 | Legacy NBFW | PMOSS_COMPASS |  |  | Code | Huei | Huei Lee |  |  | CHAUHAN, SWATI |  | SHANG, WEN | 17.02 Post Production Changes for increasing length of the below 3 tables was done CONTRAIL_ERROR CONTRAIL_BGP_PEER CONTRAIL_NETWORK_ROUTING_INST Post-MD Script to update the intfc_vrsn_cnter_grp_fld_mp table needs to be implemented for these tables
1704 | 289544 | 458542 | NetBond Adv. Reports | NetBond |  |  | Code | Huei | Huei Lee |  |  | CHAUHAN, SWATI |  | SHANG, WEN | 17.02 Post Production Changes for increasing length of the below 3 tables was done CONTRAIL_ERROR CONTRAIL_BGP_PEER CONTRAIL_NETWORK_ROUTING_INST Post-MD Script to update the intfc_vrsn_cnter_grp_fld_mp table needs to be implemented for these tables
1704 | 287479 | 458774 | NOKCTSPRS summaries | VoIP |  |  | Code | Ravi | Ravi Yelesvarapu
1802 1707 | 286118 | 461651 | 9.5 (17) Telemetry Data Gen ECOMP 173 - PCP | VoIP |  |  | Cancelled | Eric | Senthil |  |  | Emily Montgomery (es9137) | Emily Montgomery (es9137) |  | 1/23: IPOR shows this project as being cancelled 4/28: Project is on hold 3/5: Srinivas and Eric attend the story review meeting 3/4: Didi sent out an invite for a meeting tomorrow to do the US reviews
1712 1710 1707 | 294356A-M 294356-M 294356-M | 462944 | FirstNet Pre-award - Service Enablement | Mobility |  |  | Code | Eric | Senthil (DM, MD) Manish (DMaaP, DM, MD) Wes (DM, MD) | IT8.1.1 7/3/2017 - 7/14/2017 IT8.1.2 7/17/2017 - 7/28/2017 IT8.2.1 7/31/2017 - 8/11/2017 IT8.2.2 8/14/2017 - 8/25/2017 IT8.3.1 8/28/2017 - 9/8/2017 IT8.3.2 9/11/2017 - 9/18/2017 OLD schedule as of 7/7 due to IT split shown above IT7.1 4/10/2017 - 5/8/2017 IT7.2 5/8/2017 - 6/5/2017 IT7.3 6/5/2017 - 7/3/2017 IT8.1 7/3/2017 - 7/31/2017 IT8.2 7/31/2017 8/28/2017 OLD Schedule IT7.1 4/10/2017 - 5/1/2017 IT7.2 5/1/2017 - 5/22/2017 IT7.3 5/22/2017 - 6/12/2017 IT7.4 6/12/2017 - 7/3/2017 IT8.1 7/3/2017 7/24/2017 IT8.2 7/24/2017 8/14/2017 IT8.3 8/14/2017 9/4/2017 IT8.4 9/4/2017 9/25/2017 |  | Erica Chao (ec698j) | Erica Chao (ec698j) | Nasreen Habib (nh8987) Jasper Tong (jt1044) |  | All DMs have been materialized and project is ready to deploy.
1802 1712 | 294356B-M | 462944 | FirstNet Core Infrastructure OSS Part 3 - 294356b | Mobility |  |  | Code | Eric | Srinivas (MD) Alan / Patricia (KPI engine) | ? |  | Erica Chao (ec698j) | Erica Chao (ec698j) | Jasper Tong (jt1044) | 10/19: This work will be done only in dev. Waiting on green light from Jasper to do this work. 10/18: Jasper reviewed a new Guest OS requirement today. Srinivas & Eric attended. The story will be created tomorrow. Below is the schedule: 11/11/2017 - Complete development 11/17/2017 - ST HO | All DMs have been materialized and project is ready to deploy.
1710 1707 | 294356-V | 462944 | FirstNet Pre-award - Service Enablement | VoIP |  |  | Code | Eric | Senthil (DM, MD) Manish (DMaaP, DM, MD) Wes (DM, MD) Patricia (KPI engine) Gourav (DM, MD) | IT 1 7/26/2017 - 8/15/2017 IT 2 8/16/2017 - 9/5/2017 Old iterations IT7.1 4/10/2017 - 5/1/2017 IT7.2 5/1/2017 - 5/22/2017 IT7.3 5/22/2017 - 6/12/2017 IT7.4 6/12/2017 - 7/3/2017 IT8.1 7/3/2017 7/24/2017 IT8.2 7/24/2017 8/14/2017 IT8.3 8/14/2017 9/4/2017 IT8.4 9/4/2017 9/25/2017 |  | Kris Hubble (wh4355) | Kris Hubble (wh4355) | Ed Berberich (eb1847) |  | All DMs have been materialized and project is ready to deploy.
1712 | 294356A-V | 468645 | FirstNet Core Infrastructure OSS Part 2 | VoIP |  |  | Code | Eric | Manish (DMaaP, DM, MD) Wes (DM, MD) Patricia (DM, MD, KPI engine) Kshama (DM, MD) | IT1 9/6/2017 - 9/26/2017 IT2 9/27/2017 - 10/18/2017 |  | Kris Hubble (wh4355) | Kris Hubble (wh4355) | Ed Berberich (eb1847) | 8/15: Ed informed Eric about this new 1712 project today via Q | All DMs have been materialized and project is ready to deploy.
1802 | 294356B-V | 469039 | VoIP FirstNet Core Infrastructure OSS Part 3 - 294356b | VoIP |  |  | Code | Eric | Kshama (DM, SQL) | IT1 11/29/2017 - 12/19/2017 IT2: 12/20/2017 - 1/9/2017 |  | Kris Hubble (wh4355) | Kris Hubble (wh4355) | Ed Berberich (eb1847) | 11/27: Srinivas and Eric worked on finalizing the tasks today. Work will be assigned to Kshama so that she can be the CDR SME replacement for Wes. Eric informed Kshama via Q so she can see this work assigned to her when she returns from vacaton on 12/11. Iterations are IT1 11/29-12/19 & IT2: 12/20-1/9. Herb Rottner's backup will be June first backup, then Ming-Ming Yu and Jeff Stein 11/22: WKH(2:34:19 PM): you have 6 user stories, the next dev iteraton starts on Nov 29 and goes to Dec 19. Can you do them all in that time frame or do you need another iteration. Eric Gonzalez (eg7567)(2:36:47 PM): Give me a minute to check Eric Gonzalez (eg7567)(2:36:55 PM): Need to wrap up something first WKH(2:36:58 PM): ok Eric Gonzalez (eg7567)(2:46:53 PM): I don't think we can complete the work this year. I'll need an iteration that ends in January 2018. Regardless, I'll still search for an experienced CDR developer to do this work which is very complicated and very time consuming. CDR work is never easy WKH(2:50:36 PM): I'll need to discuss this with ST. The next iteration would be Dec 20 - Jan 9. That would only leave 3 1/2 weeks for testing. You will need to try to handoff earlier than Jan 9 if possible due to the time constraints. Eric Gonzalez (eg7567)(2:53:03 PM): Due to the holidays, everyone being on vacation, losing 2/3 of my team we cannot deliver earlier than 1/9/2018. Let me discuss this with my team and see who has bandwidth. 11/20: Herb continued this story review. Srinivas and Eric attended. 11/17: Herb Rottner & June Shi reviewed their stories with Srinivas and Eric. Eric made it clear that if the dev w ork is due in 2017 then we do not have resources and will not be able to commit; | All DMs have been materialized and project is ready to deploy.
1707 | 295862 | 464452 | 1707 Critical Features Project for vUSP and pUSP | VoIP |  |  | Code | Eric | Senthil (DMaaP, DM, MD) Manish (DM, MD) | R07.1 2017-05-02 Std W 3w (2017-04-12 TO 2017-05-02) R07.2 2017-05-23 Std W 3w (2017-05-03 TO 2017-05-23) R07.3 2017-06-13 Std W 3w (2017-05-24 TO 2017-06-13) | [5 empty] | All DMs have been materialized and project is ready to deploy.
1710 | 295862A | 468252 | 1707 Critical Features Project for vUSP and pUSP - 295862a | VoIP |  |  | Code | Eric | Srinivas (Dmaap, DM, MD) Patricia (DMaaP), MD) | IT3 8/16/2017 - 9/5/2017 IT4 9/6/2017 - 9/26/2017 |  |  | Subrahmanyam Jonnavittula (sj896b) | Deepa Saxena (ds521a) | 8/15: Srinivas & Eric met with Deepa Saxena to review this story | All DMs have been materialized and project is ready to deploy.
1806 | 293586 | 464839 | VPMS Backend & DB - Wave 2 | VoIP |  |  | Code | Eric | Patricia (DM, MD, KPI engine) | IT1: 12/18/2017 - 1/12/2018 IT2: 1/15/2018 - 2/9/2018 IT3: 2/12/2018 - 3/9/2017 IT4: 3/12/2018 - 4/6/2018 IT5: 4/9/2018 - 5/4/2018 IT6: 5/7/2018 - 6/1/2018 |  | Janet Perrineau | Janet Perrineau | Suryaprakash Mareddy | 1/19: Eric created the tasks in TDP today 1/19: Erica pushed out the entire IT schedule by 1 week. Eric adjusted the dev due date in this file accordingly. 1/17: Surya held a meeting to discuss the 3 single row raw data calculated columns. It was decided to NOT add these columns into the raw tables. AA56 1/16: Surya will discuss the same row calculations with Hui-Tung today and see if VEC/VCC can do it. Will set up a meeting with VETL/Vertica only if VEC/VCC cannot do this. 1/10: Surya held a meeting to determine who should do the same row calculations but it was not resolved. 1/9: Erica Chao is taking over this project from Janet. Iteration schedule was provided. 12/12: In a 2nd story review meeting later today, Janet said that if we have to go into IT 2 then that is fine but try to deliver early in IT2. Eric said that is more realistic for VETL/Vertica. 12/12: Eric attended Surya's story review meeting. Janet provided the IT1 dates of IT 12/18/2017 - 1/12/2018. I told Janet that no development can begin until 2018 due to vacations and that we MIGHT be able to deliver a few days AFTER 1/12/2018. 12/11: Eric decided to assign this project to Patricia instead of Abhishek. Once the developers in Eric's domain run out of bandwidth, then we'll assign projects to Abhishek. 12/11: Eric attended this meeting alone. Found out that Abhishek is located offshore. The VETL/Vertica stories were not reviewed and will be reviewed tomorrow (12/12) 12/11: Eric forwarded story review meeting to Abhishek since he will be assigned to this project. 12/8: Suryaprakash Mareddy scheduled a story review meeting for 12/11 12/5: Janet scheduled the kick off call for 12/6. Eric declined the invite and sent email to Janet to move this meeting to next week after 1712 deployment is over. 11/17: Janet sent email saying this project is ready for story reviews. The reviews will begin on 11/27/2017. 6/1: Eric asked Janet via Q to add him into all related meetings. They are still gathering requirements and no ETA on story review meeting yet. 5/31: Dana informed Eric that this project was assigned to Toni Q but should be assigned to Eric. Eric reassigned it to himself today in iPOR
1710 | 296115A | 466050 | T07 72e Design Platform Enh ECOMP 173 (ID 296115a) | Mobility |  |  | Code | Eric | Manish (DM) Gourav (DM, MD, loads) Wes (Logic, loads, MD, DIT) Sachin/Wes (Logic, loads, MD, DIT) Patricia (DMaaP, CSV script) | IT42 5/8/2017 - 6/2/2017 IT43 6/5/2017 - 6/30/2017 IT44 7/3/2017 - 7/28/2017 | Sachin Sahai (ss669t) | Swati Chauhan (ss3064) | Swati Chauhan (ss3064) | Wen Shang (ws4361) | 6/8: This project will be used for the CTI/DTI migration to AAI for getting AAI IM data | All DMs have been materialized and project is ready to deploy.
1711 1712 | 296115B | 467974 | T07 72e Design Platform Enh ECOMP 173 (ID 296115a) | Mobility |  |  | Code | Eric | Wes (DM, MD) | IT42 5/8/2017 - 6/2/2017 IT43 6/5/2017 - 6/30/2017 IT44 7/3/2017 - 7/28/2017 | Sachin Sahai (ss669t) | Swati Chauhan (ss3064) | Swati Chauhan (ss3064) | Wen Shang (ws4361) | 10/16: This 1712 project is being deployed early in 1711 | All DMs have been materialized and project is ready to deploy.
1710 1707 | 295922 | 464446 | MOG release 11.1 and migration to AIC 3.0 | Mobility |  |  | Code | Eric | Patricia (DMaaP, DM, MD) Gourav (KPI engine) | IT8.1 7/3/2017 – 7/28/2017 IT8.2 7/31/2017 – 8/25/2017 IT8.3 8/28/2017 – 9/22/2017 |  | Janet Perrineau (jp6581) | Janet Perrineau (jp6581) | Justine Lau (jl905g) | 6/6: Justine reviewed this story today 6/1: Justine Lau had a story review meeting today. 4/6: Eric checked iPOR and noticed this project moved from 1707 to 1710. 3/15: Tony assigned this project to Eric in his iPOR spreadsheet. | All DMs have been materialized and project is ready to deploy.
1802 | 299184 | 467687 | MOG 12 Release for FirstNet | Mobility |  |  | Code | Eric | Patricia (DMaaP, DM, MD, KPI engine) | R09.1 9/25/2017 - 10/21/2017 R09.2 10/23/2017 –11/17/2017 R09.3 11/20/2017 – 12/15/2017 |  | Janet Perrineau (jp6581) | Janet Perrineau (jp6581) | Justine Lau (jl905g) | 9/12: Eric created that tasks in TDP. Janet provided the IT schedule. 8/23: Eric created the tasks ONLY in this file and provided Justine Lau an estimate of 2.5 weeks for ONLY development time. She'll need to double the estimate to account for meetings, ST HO and deployment. Eric will create these tasks in TDP once the grooming meeting takes place. 8/22: Srinivas & Eric attended the story review meeting. Development must begin next week. 8/21: Justine informed Eric of this project. Story review will be tomorrow. | All DMs have been materialized and project is ready to deploy.
1802 | 298479 |  | T11 11.3f Labs and Tech Dev Package | VoIP |  |  | Cancelled | Eric | [6 empty] | 1/23: IPOR shows this project as being cancelled 10/19: Project is on hold in iPOR 6/21: Eric noticed this project in Dana's staffing file. iPOR shows that it's a DCAE project so it would be assigned to Eric
1707 | 290426b |  | ADTM R3 Qos OnDemand (MCS 2.2.1 Neo Enterprise) | MOBILITY |  |  |  | Toni | Dev Lead: Rajesh DM/MD: Rajesh |  |  | Terri Marhoffer |  |  | 6/19: ST HO complete
1707 | 297100 | 465521 | New Day PE Service Assurance (DriveNet) | COMPASS/L3 |  |  |  | Toni | Dev Lead: Zhenyuan DM/MD: Zhenyuan |  |  | Lon Tanner |  | Stephen Lam | 6/16: ST HO complete.
1707 | 295752 | 463927 | Nokia (ALU) MME WM 10.1 via SAM EMS | MOBILITY |  |  |  | Toni | Dev Lead: Rajesh DM/MD: Rajesh |  |  | Steven Rivenburg (sr807g) |  | PARTHASARATHY, KANNAIYAN | 6/21: ST HO complete.
1707 | QH-MS-170706 |  | Ops request for ASE and Sundance raw PM feeds | MOBILITY |  |  |  | Toni | Dev Lead: Rajesh DM/MD: Rajesh |  |  | Terri Marhoffer |  |  | 6/16: ST HO complete.
1707 | 297108 | 465579 | Nokia FSM4 Delta - NOKEUTRAN (w/DN Mapping Removal) | MOBILITY |  |  |  | Toni | Dev Lead: Rajesh DM/MD: Rajesh |  |  | Steven Rivenburg (sr807g) |  | PARTHASARATHY, KANNAIYAN | 6/23: ST HO complete.
1707 | 297102 | 465580 | Nokia NetAct 17.2 P8 (Delta)- NOKNETACT (w/successful loading) | MOBILITY |  |  |  | Toni | Dev Lead: Rajesh DM/MD: Rajesh |  |  | Steven Rivenburg (sr807g) |  | PARTHASARATHY, KANNAIYAN | 6/18: ST HO complete.
1708 | 298471 |  | Ericsson L17.Q2 (PMATT #249277) (aka E/// EUTRAN) | MOBILITY |  |  |  | Toni | Dev Lead: Rajesh DM/MD: Rajesh |  |  | Steven Rivenburg (sr807g) |  | Rama Ati | 6/26: DA and layouts complete. Development to begin.
1709 | 296455 | 462872 | Nokia (ALU ) MS EC LR16.1-SC SW Upgrade (#239102) (aka ALU METROCELL) | MOBILITY |  |  |  | Toni | Dev Lead: Rajesh DM/MD: Sameer, Tran, Manish |  |  | Steven Rivenburg (sr807g) |  | LiChen Tan
1710 | 297100 | 465521 | New Day PE Service Assurance | COMPASS/L3 |  |  | Code | Toni | Dev Lead: Kshama DM/MD: Kshama |  |  | Lon Tanner |  | Stephen Lam
1711 | 297108a | 465579 | Nokia FSM4 Delta - PMATT # 237117 (w/DN Mapping Removal) | MOBILITY |  |  |  | Toni | Dev Lead: Rajesh DM/MD: Surendar |  |  | Erica Cho
1806 | 289865 | 457984 | NexGen SeGW for AIC | MOBILITY |  |  |  | Toni | Dev Lead: Rajesh DM/MD: Rajesh |  |  |  |  | Jiya Peng
18?? 1802 1710 | 283554D | [5 empty] | On Hold | Eric | [6 empty] | 1/4: The formerly PID 284146 and now either 283554D or 30087. Ken Loveless (kl4500) held a kickoff meeting today. Not sure if the work from April 2017 from 283554D is being done in this new project or not. 4/11: The project has been placed on hold 3/28: Didi told Wes that this story is moved from 1707 Metaswitch 284146 to 1710 283554D. Eric to gather project details. 3/22: Start asking Wes for statuses 3/22: Eric informed Emily to move this US to IT5 today via Q 3/17: Eric created the tasks in Rally today. Eric needs to inform Emily of the IT for this US. IT5 was chosen to allow CTI to complete their work in IT4. 3/17: US663291 was merged into this US663289 and Didi deleted US663291 3/17: Eric & Wes attended Didi's US review meeting today for TVSP IM data
1802 | 294081 | 467072 | WPS NGN LTE/VoLTE - RAN and EPC end to end priority (WPS on LTE Part 2) | VoIP |  |  | Code | Eric | Jerome (DMaaP) Srinivas (EE) |  |  | Yashika Johnson (yj838p) Bruce Coomes (bc8949) | Yashika Johnson (yj838p) Bruce Coomes (bc8949) | Raghava Vanguri (rv0604) | 10/19: Funding approved. Eric needs to create the tasks. 10/18: Raghava is still working on getting funding. DO NOT start working on this yet. 10/18: Srinvas & Eric attended Venkatesh (vc036s) and Ashok Beerman (ab4746) requirement (in Word doc) discussion. Eric provide 2 pwks of pure development so 8 wks should be used to account for meetings, ST HO, deployment, etc. 3/15: Tony assigned this project to Eric in his iPOR spreadsheet. | All DMs have been materialized and project is ready to deploy.
1810 1710 | 284526 | [5 empty] | On Hold | Eric | [6 empty] | 4/6: Project is on hold in iPOR Srinvas thinks this is Erics project. Eric will look in iPOR
1806 1802 1710 1707 | 294187 | [5 empty] | On Hold | Eric | [6 empty] | 1/23: IPOR shows this project is not for 1806 5/3: Yashika sent email stating that this project is pushed to 1802 4/6: Eric asked Yashika when story review meetings will being. Yashika said that it moved from 1707 to 1710 and the stories are not ready yet. 3/15: Tony assigned this project to Eric in his iPOR spreadsheet. Yashika will be the scrum master.
1806 1710 | 287479CO | [5 empty] | On Hold | Eric | [6 empty] | 3/15: Tony assigned this project to Eric in his iPOR spreadsheet.
1707 | 296528 | 464093 | FlexWare TDM Plugin | ? |  |  | TSO | Eric | NA | [5 empty] | 4/27: Eric asked Sasha Ng via Q when this story review will take place. Sasha said that since VETL/Vertica is TSO then there is nothing for us to do. 3/17: Tony assigned this project to Eric in his iPOR spreadsheet. | TSO, nothing to deploy
1707 | 284980 | 456848 | IPFR over BB and OTT | ? |  |  | TSO | Eric | NA | [5 empty] | 4/27: Eric asked Subrahmanyam Jonnavittula via Q when this story review will take place. Subrahmanyam said that since VETL/Vertica is TSO then there is nothing for us to do. 3/17: Tony assigned this project to Eric in his iPOR spreadsheet. | TSO, nothing to deploy
1806 1802 | 293840 | 464456 |  |  |  |  | On Hold | Eric | [6 empty] | 1/23: IPOR shows this project is now for 1806 4/28: Tony informed Eric of this 1802 project going on hold. I check iPOR and it seems to be a USP project so it would have been assigned to me.
1806 1802 1710 | 293068A | 464486 |  |  |  |  | On Hold | Eric | [6 empty] | 1/23: IPOR shows this project is now for 1806 5/15: Eric submitted the FUSE request and was declined bc the project is not ready for work to begin. Jane confirmed and asked me to not begin work yet. 5/8: Srinivas and Eric attended Minsky's story review meeting today.
1710 | 289479 | [5 empty] | Cancelled | Eric | [6 empty] | 6/21: Eric noticed this project in Dana's staffing file. iPOR shows that it's a DCAE project so it would be assigned to Eric | Cancelled
1712 | 299493 | 467226 | 2017 NSS - mS - Performance Management | VoIP |  |  | Code | Eric | Alan (KPI engine, DM) Patricia (KPI engine, DM) | 8.1 7/5/2017 - 7/25/2017 8.2 7/26/2017 - 8/15/2017 8.3 8/16/2007 - 9/5/2017 8.4 9/6/2007 - 9/26/2017 8.5 9/27/2007 - 10/17/2017 |  | Jane Eisenmann (je3134) | Jane Eisenmann (je3134) | Fani Popovici (sp975x) | 7/13: Srinvias and Eric attended Jane's grooming session today. This story was accepted and assigned to Kshama since the VoIP domain developers don't have bandwidth. 7/6: Fani will create the story in TDP tomorrow 7/5: Eric, Alan, Patricia & Srinivas attended the story review meeting but no VETL/Vertica story was reviewed today. 6/21: Eric received an invite for this project from Srinivas Bhadriraju (forwarded to Eric by Suhakar). 1st status call is today. Eric had the below Q discussion with Tony. Eric(12:29:23 PM): Hello. Who is the mobility lead for this project? See highlighted section. Eric(12:29:25 PM): Tony(12:29:50 PM): Toni Q for now Tony(12:29:57 PM): is there an issue with it? Tony(12:30:00 PM): or somebody just asking? Eric(12:30:15 PM): Ok. I'm the lead for the VoIP part so then both of us will be working on this project Tony(12:30:25 PM): ok Eric(12:30:34 PM): I just got the invite for that project so just needed to check Eric(12:30:44 PM): Toni is not on the invite so I'll forward it to her Tony(12:30:53 PM): ok Eric(12:30:53 PM): I'll update iPOR to reflect the above Eric(12:30:55 PM): thanks Tony(12:30:58 PM): np | All DMs have been materialized and project is ready to deploy.
1712 | 299492 | 467182 | 2017 NSS - mS - ECOMP Domain | VoIP |  |  | Code | Eric | Patricia (KPI engine, DM) | 1: ??9/26/2017 - 11/17/2017?? |  | Jane Eisenmann (je3134) | Jane Eisenmann (je3134) | Fani Popovici (sp975x) | 9/6: Per Jane, development will begin on 9/26 at the earliest. Still waiting for Xinyu to review additional stories. Eric provided 2 pwks estimated for ONLY Fani's story. 9/5: Srinivas & Eric attended Fani's story review meeting today. Eric tried to create the tasks in TDP but does not have TDP permissions. Asked Jane Eisemann to grant him access. Still waiting for the grooming meeting to assign the work to an iteration. Informed Patricia that this work is being assigned to her. | All DMs have been materialized and project is ready to deploy.
1710 | 291247B | 466020 | NoD - Move to AIC3 0&nbsp; Features&nbsp;&nbsp; testing | VoIP | Broadworks AIC3.x | D2.0 | Code | Eric | Wes (Script) Srinivas (DMaaP, MD) Patricia (DM,MD | IT1: 7/3/2017 - 7/16/2017 IT2: 7/17/2017 - 7/30/2017 IT3: 7/31/2017 - 8/27/2017 IT4: 8/28/2017 - 9/24/2017 |  | Sasha Ng (sn061h) & Lon Tanner (lt4902) | Sasha Ng (sn061h) & Lon Tanner (lt4902) | Stephen Lam (sl679r) Wen Shang (ws4361) Paul G Madarasz (pm1439) | 6/27: Stephen reviewed this story today 6/23: Wen Shang reviewed the story today. Wes and Eric attended the meeting. 6/19: Sasha Ng Qd Eric about this project to find out which lead will be assigned to it. Since iPOR shows the "Application" as "DCAE" then I think it would be assigned to me. | All DMs have been materialized and project is ready to deploy.
1712 | 291247C | 468982 | VCE VPE on AIC 3x Resiliency and Scaling | VoIP | Juniper VPE | D2.0 | Code | Eric | Manish (DMaaP, DM, MD) | IT1: ??10/1/2017 - 10/25/2017?? |  | Lon Tanner(lt4902) | Lon Tanner(lt4902) | Stephen Lam (sl679r) | 10/24: This project will NOT deploy in 1711 anymore and will be deployed in 1712. 10/12: This project will need to be deployed early in 1711 | All DMs have been materialized and project is ready to deploy.
1707 | 294728 | 464374 | SAREA IPv6 | L3 |  | CTI | Code | Huei | Huei
1707 | 297458 | 465551 | eNodeB Reboot |  |  |  | Code | Sudhakar | Zhenyuan (Export Engine, DM) |  |  | Terri Marhoffer |  | Rakhee Nair
1709 | 295511A | 467040 | Enhanced Mobile (R2b) - Frictionless Automation XSP Support | VoIP |  | BW XSP | Code | Eric | Patricia (MD, DIT) | R08.1 7/5/2017 - 7/25/2017 R08.2 7/26/2017 - 8/15/2017 R08.3 8/16/2017 - 9/5/2017 |  | Jane Eisenmann (je3134) | Jane Eisenmann (je3134) | Yusef Bisrat (YB4820) | 7/20: Eric, Srinivas and Wes attended the grooming meeting 7/13: Wes, Srinivas and Eric attended Yusef's story review meeting today. The stories were accepted. | This project is test only for VETL/Vertica so there is NOTHING to deploy. We just need to validate that files are provided and loading as expected.
1712 | 295511A | 466585 | Enhanced Mobile (R2b) - Frictionless Automation XSP Support | VoIP |  | BW XSP | On Hold | Eric | Alan (DM, EE) |  |  | Jane Eisenmann (je3134) | Jane Eisenmann (je3134) | June Shi (ys1362) Cho Wong (cw1728) | 10/17: Still no funding. Cho is trying to get funding for 1712 or 1802. | Project is on hold. This project is test only for VETL/Vertica so there is NOTHING to deploy. We just need to validate that files are provided and loading as expected.
1709 | 294042 | 459627 | Nokia (ALU) 16.2 RD 459627 | Mobility |  |  | Code | Toni | Dev Lead: Rajesh DM/MD: Manish/Senthil |  |  | Steven Rivenburg (sr807g) |  | PARTHASARATHY, KANNAIYAN
1710 1802 | 290995 | 457421 | AIC - vFW Development (GT4F.01) - 3Q (1610) - PAN vIPR | DCAE |  | VCC | On Hold | Huei | Zhenyuan Shi |  |  | kp2636" |  | Alan Gale
1804 | 284834a | 465973 | Next Gen Architecture - D1 Intermediate Solution | L3 |  | PEC | Code | Huei | Huei Lee |  |  | Jane Chung | Jane Chung | Jeff Yu
1710 | 292563b | 462090 | AIC - Certification of Jericho within AIC (Part 3) | DCAE |  | VCC | On Hold | Huei | Huei Lee |  |  | Jane Chung | Jane Chung | Jeff Yu
1710 | 294728a | 464852 | SAREA on Domain 2 | L3 |  | PEC | Code | Huei | Zhenyuan Shi |  |  | Jane Chung | Jane Chung | Alan Gale
1710 | 296117a | 466577 | 296117a - Updating Logging Specs continued (OpenStack) | DCAE |  | CAS | Code | Huei | Huei Lee |  |  | Amar Gurajapu | Amar Gurajapu | Wen Shang, Sujay Kumar Mereddy
1710 | 297100 | 464050 | New Day vPE Service Assurance and Delivery (iTAS Drivenet) | L3 |  | VCC | Code | Huei | Huei Lee |  |  | Cynthis Nord | Cynthis Nord | Jeff Jaggernauth
1710 | QH-MS-177001 | 457521 | PMOSS-Compass (CTI) to resync the topology tables with PEC and Compass Collectors | L3 |  | CTI | Code | Huei | Zhenyua Shi |  |  | Jane Chung | Jane Chung | Jeff Yu
1710 | 295246 | 463513 | Customer Experience Enhancement Release 4 | NetBond |  | NBO | Code | Ravi | Ravi Yelesvarapu, Huei Lee |  |  | Kurt Smith | Kurt Smith | Kushal Jain
1806 | 295793 | 471729/463205 | ADIG on vPE FFA and OSS/BSS development Release 1a | DCAE |  |  | code | Huei | Huei/Zhenyuan |  |  |  | Lon Tanner | Paul Madarasz
1711 | 299166 | 468067 | Ericsson 17.Q3 SW Update | Mobility |  |  | Code | Toni | Dev Lead: Rajesh DM/MD: Kshama |  |  | Steve Rivenburg |  | Jiya Peng
1710 | 295842 | 464827 | Certification Project: Ericsson vMME Certification with Ericsson RAN (NFV) | Mobility |  |  | Code | Toni | Dev Lead: Rajesh DM/MD: Rajesh, Surendar, Nag |  |  | Steve Rivenburg |  | Jasper Tong
1711 | 294356-M | 462944 | FirstNet Pre-award - Service Enablement | Mobility |  |  | Code | Toni | Dev Lead: Rajesh DM/MD: Rajesh, Tran, Sameer, Surendar |  |  | Erica Chao (ec698j) |  | Nasreen Habib (nh8987) Jasper Tong (jt1044)
1711 | 294042 | 459627 | Nokia (ALU) 16.2 RD 459627 | Mobility |  |  | Code | Toni | Dev Lead: Rajesh DM/MD: Sameer |  |  | Steve Rivenburg | Partha
1712 | 294356-M | 462944 | FirstNet Pre-award - Service Enablement(vpas only) | Mobility |  |  | Code | Toni | Dev Lead: Rajesh DM/MD: Tran |  |  | Erica Chao (ec698j) |  | Nasreen Habib (nh8987) Jasper Tong (jt1044) |  | Ready for deploy. vPAS technology only.
1712? | 294173 | 463324 | ABS Environment Purchase: Request development resources | MOBILITY |  |  | Test Only | Toni | Dev Lead: Rajesh | [6 empty] | Project delayed. Test platform only.
1804 | 297100a |  | New Day vPE Service Assurance and Delivery | COMPASS/L3 |  |  |  | Toni | Dev Lead: Rajesh DM/MD: Sameer |  |  | Esmat |  |  | 11/2: waiting on unapproved VPMO per Esmat
1712 | 299097 | 468158 | Ericsson MME 1.8 Software Upgrades (PMATT# 253940) | Mobility |  |  | Code | Toni | Dev Lead: Rajesh DM/MD: Surrender |  |  | Steve Rivenburg |  | Partha |  | Ready for deploy.
1804 | 294739d | 463935 | FirstNet OSS Support | Mobility |  |  | Code | Toni | Dev Lead: Rajesh DM/MD: Surrender, Tran |  |  | Bonita Petrus |  | Srividya Bhimireddy
1802 | 296151A | 467998 | T07 72c PSD TechOps ECOMP Theme 7 Package 1 - 296151a | Mobility | ? | ? | Code | Eric | Kshama (DM, MD) Jerome (DMaaP) | ? |  | Swati Chauhan (ss3064) | Swati Chauhan (ss3064) | Min Chen (mc4381) | 10/19: Swati is still trying to get the funding approved 10/16: Eric sent Swati an email stating that we CANNOT commit to 11/17/2017. Instead, we can commit to 12/8/2017 10/13: Need to discuss if we can deliver by 11/17 or not. Need to let Swati know if we commit. If we cannot commit the provide a date of when we can truly deliver. 10/11: Swati held a grooming meeting. Eric told Swati that stories are not ready especially since we found out at the very end of the last review meeting that the JSON message will be provided via DMaaP MR and NOT DR which changes many concerns already discussed. 10/6: Min had a continuation meeting. We fully understand the requirement now. 9/21: Srinivas & Eric attended Min Chen's story review today. Didn't finish all stories and Min will schedule a contuation call when he returns on 10/2. 9/21: Min Chen told Eric that he will hold a story review tomorrow | All DMs have been materialized and project is ready to deploy.
1806 | 301267 301367 | 470524 or 471913 | T07 72c PSD TechOps ECOMP Theme 7 Package 1 - 296151a | Mobility | ? | ? | Code | Eric | Kshama (DM, MD) | DEV: IT49: R10.3 2/12/2018 – 3/12/2018 IT50: R11.1 3/12/2018 – 4/9/2018 IT51: R11.2 4/9/2018 – 5/7/2018 IST: ITR 49: 3/26 Mon – 4/06 Fri (2 wks) ITR 49: 50: 4/09 Mon – 5/04 Fri (4 wks) ITR 49: 50,51: 5/07 Mon – 6/08 Fri (5 wks) |  |  |  | Shau-ann Chang (sc790u) | 1/29: Shau-Ann held a meeting to review the overall project 1/24: Shau-Ann Chang (sc790u) sent a story review invite that will take place on 1/29/2018. | All DMs have been materialized and project is ready to deploy.
1802 | 295491A | 468010 | T10 10 3 - Tenant Isolation and enabling testing in production (172) - 295491a | VoIP | ? | ? | Code | Eric | Jerome (DMaaP) Sameer (DMaaP, DM, MD, DIT) | ? |  | Swati Chauhan (ss3064) | Swati Chauhan (ss3064) | Mingming Yu (my2263) | 10/18: Manish will begin working on this on Monday 10/17: Eric created the tasks in TDP today. Already discussed this work with Manish on Monday. Informed Manish today via Q that tasks are now in TDP. 10/12: Mingming Yu had the story review meeting. She used 4 pwks for our work. Eric will need to confirm. 10/10: Mingming Yu has a story review meeting scheduled for 10/12 | All DMs have been materialized and project is ready to deploy.
1802 | 300375 | 468150 | DNS Based Routing for Network Element Addressing | VoIP | Broadsoft VNI AS | D1 | Code | Eric | Patricia (DM, MD, DMaaP) | IT 9.2 10/18/2017 - 11/7/2017 IT 9.3 11/8/2017 - 11/28/2017 IT 9.4 11/29/2017 - 12/19/2017 |  | Subrahmanyam Jonnavittula (sj896b) | Subrahmanyam Jonnavittula (sj896b) | Deepa Saxena (ds521a) | 10/19: Eric needs to provide estimate to Deepa by Monday. Provided a generic 3 pwks for now. 10/19: Deepa reviewed the work that we need to do. Will create the stories 10/18: Deepa will hold a meeting tomorrow to discuss the below: The SE team had a meeting today and the direction from Mike F and Trey is to migrate the data from DataStor to Vertica. So, I need help in figuring out the estimate for this work. Please join this call so I can move forward. | All DMs have been materialized and project is ready to deploy.
1802 | 294728b | 464853 | PMOSS-Compass support new and updated reports for Capacity Management | DCAE | CTI, VCC |  | Code | Huei | Huei, Zhenyuan |  |  | Jane Chung | Jane Chung | Alan Gale
1712 | 293640a | 465476 | Support for 10Gb S Line-rate phase 2 | MOBILITY |  |  | Test Only | Toni | Dev Lead: Rajesh DM/MD: Sameer/Tran |  |  | Julius Sheppard |  | Xinyu |  | Ready for deploy. Test only.
1802 | 299682 |  | Metro Open ROADM R1802 | DCAE |  |  |  | Toni | Dev Lead: Rajesh DM/MD: Surender
1802 | QH-1802001 | 463935 | Firstnet Juniper CCS & SDG Routers vertical format | MOBILITY |  |  |  | Toni | Dev Lead: Rajesh DM/MD: Surender
1806 | 293586 |  | VPMS Backend & DB - Wave 2 | Mobility & VoIP |  |  | Code | Eric | Patricia (DM, MD, KPI engine) | IT49 2/5/2018 - 3/2/2018 IT50 3/5/2018 - 3/30/2018 IT51 4/2/2018 - 4/27/207 |  |  | Erica Chao (ec698j) | Suryaprakash Mareddy (sm8290) | 12/12: In a 2nd story review meeting later today, Janet said that if we have to go into IT 2 then that is fine but try to deliver early in IT2. Eric said that is more realistic for VETL/Vertica. 12/12: Eric attended Surya's story review meeting. Janet provided the IT1 dates of IT 12/18/2017 - 1/12/2018. I told Janet that no development can begin until 2018 due to vacations and that we MIGHT be able to deliver a few days AFTER 1/12/2018. 12/11: Eric decided to assign this project to Patricia instead of Abhishek. Once the developers in Eric's domain run out of bandwidth, then we'll assign projects to Abhishek. 12/11: Eric attended this meeting alone. Found out that Abhishek is located offshore. The VETL/Vertica stories were not reviewed and will be reviewed tomorrow (12/12) 12/11: Eric forwarded story review meeting to Abhishek since he will be assigned to this project. 12/8: Suryaprakash Mareddy scheduled a story review meeting for 12/11 12/5: Janet scheduled the kick off call for 12/6. Eric declined the invite and sent email to Janet to move this meeting to next week after 1712 deployment is over. 11/17: Janet sent email saying this project is ready for story reviews. The reviews will begin on 11/27/2017. 6/1: Eric asked Janet via Q to add him into all related meetings. They are still gathering requirements and no ETA on story review meeting yet. 5/31: Dana informed Eric that this project was assigned to Toni Q but should be assigned to Eric. Eric reassigned it to himself today in iPOR
1802 | 298772 | 467522 | NetBond vNAT on AIC3 | DCAE | CTI, VCC, WBG |  | code | Huei | Huei, Zhenyuan |  |  | Lon Tanner | Lon Tanner | Ed Gujju/Kushal Jian
1802 | 300360 | 471827 468198 | Fast Pass - Call Redirect over VoLTE | VoIP |  |  | Code | Eric | Kshama (DM, MD) Alan (EE, DIT) |  |  | Kris Hubble (wh4355) | Kris Hubble (wh4355) | Cho Wong (cw1728) June Shi (ys1362) | 10/31: Kris held the grooming meeting today 10/27: Kris will have the grooming meeting next week. The iterations are 11/8 - 11/28 and 11/29 - 12/19 10/26: Story review continuation took place today 10/25: Cho Wong scheduled a US review meeting for 10/26 10/25: Cho moved this story into 300360. It was originally in 295511A 10/6: Cho is waiting for June to return from vacation to discuss funding. Cho will also review pseudo code from Srinivas. 9/28: Cho Wong (cw1728) will try to get funding for this project and do the work using a CR and still deliver in 1710. 9/22: Eric asked June Shi when the next review meeting will take place. June says she is still working on trying to get funding for the project. Cho Wong (cw1728) will be the backup SE while June is on vacation. 9/15: Waiting for the continuation call. Will assign this work to Manish 9/14: Wes & Eric attended June Shi's story review meeting. | All DMs have been materialized and project is ready to deploy.
1803 | 300360 | 471827 | Fast Pass - Call Redirect over VoLTE | VoIP |  |  | Code | Eric | Kshama (DM, MD) Alan (EE, DIT) |  |  | Kris Hubble (wh4355) | Kris Hubble (wh4355) | Cho Wong (cw1728) June Shi (ys1362) | 2/5: 7 out of 9 stories are pushed to 1803 deployment due to network not being ready in 1802. Eric provided the below estimates hours to pull out all requirements. Eric will confirm these estimates with Kshama & Alan. Cho Wong also discussed doing a point release for 3/10 or a defect CR for 3/10 to deploy the remaining work earlier than 1803 (3/17) depending on customer decision. - Kshama: 16 hours for DM, metadata & DIT - Alan: 8 hours for EE SQLs & DIT. 12/20: ST HO was completed and accepted 12/13: Kshama & Subra have both asked Sandeep for official files to do DIT. No response from Sandeep yet. 12/11: Kshama is waiting for VEC/VCC to publish files for DIT. She will send reminder to Sandeep Dheeravath today 11/7: Kshama completed all the work but waiting for files to be automatically published via DMaaP. No ETA 10/31: Sandeep said that he can provide the file layouts by tomorrow at the latest. 10/31: Kris held the grooming meeting today 10/27: Kris will have the grooming meeting next week. The iterations are 11/8 - 11/28 and 11/29 - 12/19 10/26: Story review continuation took place today 10/25: Cho Wong scheduled a US review meeting for 10/26 10/25: Cho moved this story into 300360. It was originally in 295511A 10/6: Cho is waiting for June to return from vacation to discuss funding. Cho will also review pseudo code from Srinivas. 9/28: Cho Wong (cw1728) will try to get funding for this project and do the work using a CR and still deliver in 1710. 9/22: Eric asked June Shi when the next review meeting will take place. June says she is still working on trying to get funding for the project. Cho Wong (cw1728) will be the backup SE while June is on vacation. 9/15: Waiting for the continuation call. Will assign this work to Manish 9/14: Wes & Eric attended June Shi's story review meeting. | All DMs have been materialized and project is ready to deploy.
1802 | 282055C | 471691 | Next Gen Virtual Route Reflector Rel 6 | VoIP |  |  | Code | Eric | Jerome (DMaaP, JSON parser) Sameer (DM, MD) |  |  | Jackie Barlow (jb0805) | Jackie Barlow (jb0805) | Andy Egan (ae3127) | 11/20: Jerome and Sameer committed to this work 11/17: Eric reviewed this work with Sameer over a meeting. Sameer understands what to do. 11/16: Jerome & Eric attended Andy Egan's story review today. No ETA on when JSON file will be provided. 11/13: Jerome informed me of this project via Q. Eric sent email to Andy Egan to schedule a story review ASAP | All DMs have been materialized and project is ready to deploy.
1802 | 298715A | 471834 or 468765 | T07 7 2c Split for Framework to Enable Users to Create Analytics - 298715a | VoIP |  |  | Code | Eric | Jerome (DMaaP) |  |  | Brian Comilang (bc255q) | Brian Comilang (bc255q) | Shrikant Acharya (sa8763) | 11/22: Brian, Jerome, Laxmi and Eric discussed dependencies. Per Laxmi, Dominic (dl715d) (who wasn't on the call) said that he will need to complete the prefix DMD/DMaaP topic work on Monday (11/27) and Laxmi will complete the suffix Global DMaaP topic work on Tuesday (11/28). Jerome will then be able to begin work on Wednesday (11/29). The drop dead date for Dominic & Laxmi to complete everything is Wednesday (11/29). Any day after that will cause a day-to-day slip for Jerome. Eric pushed the dev due date from 12/8 to 12/13 due to dependencies. Jerome will try to complete all work before 12/13/2017 or earlier. 11/21: Eric, Jerome & brian Comilang met to discuss the dev due dates. Eric stated that 12/8 is NOT doable due to dependencies. Brian will schedule a call for tomorrow to discuss dependencies with Laxmi. 11/20: Jerome & Eric attended the story review meeting today. Waiting on grooming meeting to discuss deplendencies. Jerome will work with Swapna Anne (sa9226) to get full clarity on the work. 11/16: Jerome informed Eric of this new work via Q today. Need to ask Swapna Anne (sa9226) to do a story review and grooming meeting. Eric Qd Swapna today. | Project is ready to deploy.
1802 | 298822B | 469049 | Automation - End-to-End Incident Management - Release 1 - PI 3 | VoIP |  |  | Code | Eric | Patricia (DMaaP, EE) |  |  | Theresa Siordia-Rybarski (ts1916) | Theresa Siordia-Rybarski (ts1916) | Rick Quagliata (rq2591) | 1/12: Patricia agreed to complete this work by 1/23 and do ST HO on 1/24. Rick provided all the needed info in the story for Patricia. 1/12: Eric will need to locate a developer that can complete development b y 1/23 and do ST HO on 1/24. 1/12: Rick will update this story and create a new story for the audit publishing work 1/11: Rick Quagliata (rq2591) asked if we can do the below Rick(11:52:20 AM): Hi Eric. P&CM_ENT has a project 298822b 1802 which needs a daily audit file published to data router. it will be a simple file which will contain a total for the number of alerts PACE published during the 24 hour period. The subscribing application will be sending me info on the format of this audit file soon. Sufen from PACE thought it would be better for vETL to create this file, instead of PACE. Are you on board with that? Eric Gonzalez (eg7567)(12:06:06 PM): Hi Rick. That sounds good to me. Let me confirm with another person on my team. Hold on Rick(12:09:28 PM): ok Eric Gonzalez (eg7567)(12:44:54 PM): Yes, we can do that Rick(12:45:09 PM): ok great Eric Gonzalez (eg7567)(12:45:23 PM): I see your email so I'll forward it to my team Rick(12:45:55 PM): ok. i am writing the US now. Eric Gonzalez (eg7567)(1:03:00 PM): What release is that PID for? Eric Gonzalez (eg7567)(1:03:08 PM): I cannot check right now due to being in a meeting Eric Gonzalez (eg7567)(1:05:45 PM): Oh wait... Your Q above shows 1802 Rick(1:06:30 PM): yes 1802 PID 298822b Eric Gonzalez (eg7567)(1:07:30 PM): Well, as long as we are given plenty of time to do the work. We'll discuss dates after we review your story Rick(1:07:49 PM): sure. thanks | Project is ready to deploy.
1806 | QH-MS-1804001 | vetl 471531/vertica 476634 | Support Firstnet’s high visibility | Mobility |  |  | Code | Toni | Developers: Patricia, Kshama |  |  | ? | ? | Justine Lau (jl905g) | 1/23: Eric provided a pure development estimate of 3 pwks to Justine via Q. Mentioned that the estimate will need to be multiplied by 2.5 or 3 to account for scrum calls, questions, ST HO, etc. 1/11: Justine Lau held a QH review meeting today.
1806 | 295793 | 463205 | Adding GMIS vPE to iTAS | PMOSS_iTAS |  |  | code | Huei | Huei/Zhenyuan |  |  |  | Lon Tanner | Paul Madarasz
1806 | 282055d | 471533/469760 | open DCAE to support Next Gen Virtual Route Reflector (vRR) | DCAE |  |  | Code | Huei | Huei/Zhenyuan |  |  |  | Jane Chung | Jeff Yu
1806 | 301368 | 472632/470527 | T17.13.1 DCAE Platform Evolution | DCAE |  |  | Code | Huei | Huei/Zhenyuan |  | Charles Cook |  | Swati Chauhan | Wen Shang
1806 | 294728c | 472635/470103 | SAREA Automation Optimization and Contended ETH | PMOSS_COMPASS |  |  | Code | Huei | Huei/Zhenyuan |  |  |  | Adam Beaver | Jeff Jaggernauth (jj8161)
1806 | 297122 | 471550/466778 | Robocalling TN Authentication (STIR/SHAKEN) - USP | PMOSS_VoIP |  |  | Code | Huei | Zhenyuan |  |  |  | Kris Hubble (wh4355) | Mingming Yu (my2263)
1806 | 297131A | 471516 |  |  |  |  | Code | Eric | Kshama Punj | R12.1 2018-07-01 M 4w [6/4/2018 – 7/2/2018] (Note: 18.06 release weekend is 6/09 - 6/10/18) R11.3 2018-06-03 M 4w [5/7/2018 – 6/4/2018] R11.2 2018-05-06 M 4w [4/9/2018 – 5/7/2018] R11.1 2018-04-08 M 4w [3/12/2018 – 4/9/2018] R10.3 2018-03-11 M 4w [2/12/2018 – 3/12/2018] R10.2 2018-02-11 M 4w [1/15/2018 – 2/12/2018] (Note: 18.02 release weekend is 2/10 – 2/11/18) |  |  | Jane Chung (jc1858) | Mingming Yu (my2263) | 2/28: Kshama & Eric attended Jane Chung's grooming meeting. 2/8: Eric & Srinivas attended Mingming's story review meeting 1/25: Mingming Yu (my2263) will have a story review meeting in the near future to discuss the creating and loading of the AAI SRIOV-PF table
1803 | 301786 | PMT not available | Ericsson L17.Q4 and L18.Q1 - Ericsson CD Agile 2018 | MOBILITY |  |  |  | Toni | DM/MD: Rajesh/Ravi |  |  | Steven Rivenburg (sr807g) |  | Rama Ati
1806 | 297519 | 471801 |  | VoIP |  |  | Code | Eric | Patricia Kshama Srinivas | IT50 (R11.1 2018-04-08 M 4w)  3/12/18 – 4/8/18 IT51 (R11.2 2018-05-06 M 4w)  4/9/18 – 5/6/18 |  |  | Kris Hubble (wh4355) | Deepa Saxena (ds521a) Ed Berberich (eb1847) | 3/13: Srinivas and Eric attended Deepa's 2nd story review meeting 3/12: Srinivas and Eric attended Deepa's story review meeting
1806 | 291247D | 471545 | NoD - Move to AIC3 0&nbsp; Features&nbsp;&nbsp; testing | VoIP |  |  | Code | Eric | Kshama | IT 11.1 3/23/2018 - 4/8/2018 IT 11.2 4/9/2018 - 4/20/2018 |  |  | Lon Tanner | Stephen Lam | 3/23: Srinivas & Eric attended Lon's grooming meeting. Eric pushed the dev due dates to the latest possible date which is 4/20/2018 and Kshama can do DIT earlier if possible.
1806 | 295390 | 471607/464532 | vUSP Geo-Redundancy Redesign (2+2) | DCAE |  |  | TSO | Huei
1806 | 297100a | 471713 | New Day vPE Service Assurance and Delivery ADI - 297100a | PMOSS_iTAS |  |  | Code | Huei | Huei
1806 | 297122 | 471550/466778 | Robocalling TN Authentication (STIR/SHAKEN) - USP (ID: 297122) | DCAE |  |  | Code | Huei | Kshama
1804 | 284834a | 471534 | Next Gen Architecture - D1 Intermediate Solution |  | INSIGHT |  | Code |  | Vela Rajendran |  |  | Bin Xie | Karen Lee | Bing Shao |  | Ready for deployment | CHG000004300747
1804 | 297100a | 471713 | New Day vPE Service Assurance and Delivery |  | INSIGHT |  | Code |  | Vela Rajendran |  |  | Bin Xie | Karen Lee | Chad Colopy |  | Ready for deployment | CHG000004300747
1804 | 301283 | 473795 | 17.10.1 Move to Open DCAE (ID: 301283) | Mobility |  |  | Code |  | Dev lead: Rajesh Meher

## Vacations
 | time axis 2017-12-01 to 2019-01-06
Alan | bar: 2017-12-01; 2017-12-11
Eric | bar: 2017-12-18 to 2018-01-02; 2018-07-04 to 2018-07-10
Huei
Jerome | bar: 2017-12-08; 2017-12-11; 2017-12-18; 2017-12-22; 2017-12-29
Kshama | bar: 2017-12-01 to 2017-12-08; 2018-06-06 to 2018-06-25
Manish | bar: 2017-12-15 to 2018-01-02
Nagarajan
Patricia | bar: 2017-12-11 to 2017-12-15; 2017-12-20 to 2017-12-22; 2017-12-25 to 2017-12-29
Ravi
Srinivas | bar: 2017-12-21 to 2018-01-01
Wes
Zhenyuan
Todd
Tony
Yeab Wondimu (yw7199)

## Deployment Leads
Release deployment schedule can be found at https://operations.web.att.com/sites/ConsumerITRM/IRM_Pages/Milestones.aspx
Release | Deployment Weekend | Deployment Type | Release Size | Deployment Lead | Backup Guide the deployment manager if new to deployment process Provide deployment support especially once deployment begins and during rest time Be the backup incase the deployment manager can no longer do the deployment | Mentor | Post-Prod Defects CR | DM Keeper | CR # | LAST_UPDATE_TS Date | Not available for this release
1702 | 2017-02-12 | Standard | Large | Ravi | Dana |  | Ravi
1703 | 2018-03-17 | If needed | Small | Mark | Sudhakar | Ravi or Eric | Mark
1704 | 2017-04-23 | Standard | Small to Medium | Dana/Ravi/Sudhakar | Suhakar | ? | Dana/Ravi/Sudhakar |  |  |  | Eric (will be on vacation week before deployment), Todd
1705 | 2017-05-21 | If needed | N/A | Eric | Mark | ? | Eric
1706 | N/A | If needed | N/A | Mark | Sudhakar | ? | Mark
1707 | 2017-07-16 | Standard | Large | Ravi | Huei | ? | Ravi | Eric
1708 | 2017-08-20 | Standard | Small to Medium | Toni | Sudhakar | ? | Toni | Srinivas |  |  | Todd due to finals. I need to be switched out from April, no can do that month. The reason why April & Dec is bad is GA Tech finals and I don't know if summer session ends in Aug or Sept
1709 | 2017-09-17 | If needed | Small | Mark | Eric | Eric | Sudhakar | Srinivas | CHG000004038664 | 2017-09-16
1711 1711 1710 | 11/12/2017 11/5/2017 10/22/2017 | Standard | Large | Todd | Ravi | Ravi | Todd | ? |  | 2017-11-11 | Melissa Arnoldi sent email stating that 1710 got pushed to 11/5 and 1711 is merged into 11/5 deployment
1712 | 2017-12-10 | If needed | Medium | Eric | Mark | NA | Toni | ? |  | 2017-12-09
1801 | N/A | If needed | N/A | Huei | Sudhakar | Sudhakar | Huei | ?
1802 | 2018-02-11 | Standard | Large | Ravi | Huei | NA | Ravi | ?
1803 | 2018-03-17 | If needed | Small | Mark | Sudhakar | ? | Mark | ? | CHG000004259267
1804 | 2018-04-22 | Standard | Small to Medium | Huei | Todd | ? | Huei | ?
1805 | N/A | If needed | N/A | Toni | Ravi | ? |  | ? |  |  | Huei & Mark cannot do 1805
1806 | 2018-06-09 | If needed | Large | Eric | Mark | ? |  | ? |  |  | Kshama will be on vacation
1807 | 2018-07-15 | Standard | Large | Todd | Ravi | ? |  | ? |  |  | Eric & Toni cannot do 1807
1808 | 2018-08-19 | Standard | Small to Medium | Toni | Mark | ? |  | ?
1809 | N/A | If needed | N/A | Ravi | Huei | ? |  | ?
1810 | 2018-10-21 | Standard | Large | Sudhakar | Eric | ? |  | ?
1811 | N/A | If needed | N/A | Ravi | Toni | ? |  | ?
1812 | N/A | If needed | N/A | Eric | Mark | ? |  | ?

## OLD Contacts from other systems (hidden)
Name | User ID | Role | Data
Jane Eisenmann |  | PMOSS PM
Amar Gurajapu |  | Scrum Master DCAE Trinity, vUSP
Danielle Huston |  | Scrum Master Trinity
Robert Lynch |  | Scrum Master DCAE MCR
Minsky Luo |  | SE PMOSS VOIP
Anand Shah |  | DCAE | All data for DCAE TA->TD
Steven Solomon |  | DCAE | All data for DCAE TA->TD
Wen Shang |  | DCAE | All data for DCAE TA->TD
Leo Xu |  | DCAE | All data for DCAE TA->TD
Chandrasekhar Thondikulum |  | CTI | Inventory Data
Himabindu Basireddy |  | CTI | Inventory Data
Lynn Williams |  | INSTAR | Inventory Data
Cary Hermann |  | INSIGHT | KCIs
Vinodh Pemmasani |  | vPEC | PM and TCA PM Alerts
Chia Yu |  | vPEC | PM and TCA PM Alerts
David An |  | vPEC | PM and TCA PM Alerts
Mary Keefe Hirsekorn |  | PCC | CDR
Richard Epp |  | PCC | CDR
Ningming Hua |  | PACE | DNR PM Alerts
Sufen Bai |  | PACE | DNR PM Alerts
Kenneth Martau |  | UEB | PM Alerts
Mike Verrilli |  | Vertica SME
Michael Conway |  | Vertica MATS
Jeremy Suppa |  | Vertica DBA
Prasad Musty |  | Vertica DBA
Shrikant Patil |  | Vertica DBA
Ramachandran Somasundaram |  | Vertica DBA Lead
Ravi Yelesvarapu |  | Vertica Dev
Srinivas Krishnamurthy |  | Vertica Dev
Chaojung Tang |  | Reporting Team Lead
Ling Liang |  | Test Lead PM Trinity 15.0
Latha Chandrashekariah |  | Test Lead CDR Trinity 15.10
Carlos Viegas |  | Test Gamma 15.10
Lucy Selecky |  | Test Gamma 15.11
Jack Chang | jc438g | ST Gamma 15.10 | BROCADELB', -- Automatically Loading confirmed 'JUNIPERTOA',-- Automatically Loading confirmed 'HPFLEXPERF',-- Automatically Loading confirmed 'JUNIPERCCE', -- Manually loading but Will check why it is not loading automatically 'BROCADEVNF',-- Manually loading but Will check why it is not loading automatically 'JUNUCPE', -- No files in QA0 asked Leo to send files 'VCENTER', -- Srinivas is working on it 'KVMPERF', -- Srinivas is working on it 'HITSANPERF' -- Srinivas is working on it
Jin Huang | jh1794 | ST Gamma 15.10 | BROCADELB', -- Automatically Loading confirmed 'JUNIPERTOA',-- Automatically Loading confirmed 'HPFLEXPERF',-- Automatically Loading confirmed 'JUNIPERCCE', -- Manually loading but Will check why it is not loading automatically 'BROCADEVNF',-- Manually loading but Will check why it is not loading automatically 'JUNUCPE', -- No files in QA0 asked Leo to send files 'VCENTER', -- Srinivas is working on it 'KVMPERF', -- Srinivas is working on it 'HITSANPERF' -- Srinivas is working on it
PMOSS Mobility ST DL-PMOSSMobilityST@att.com |  | ST distribution list
PMOSS-VoIP-ST DL-PMOSS-VoIP-ST@att.com |  | ST distribution list
Dave Williamson | dw2143 | DMD
Tim Culbert | tc2747 | DMD

## OLD - Vertica Feeds (hidden)
IN
PM (vPEC->vETL)
Broadsoft AS/MS/NS; PS/DBS/XSP/USS PM; AS License PM - BSXBWORK schema
Juniper DBE - JUNVDBE Schema
Ericsson BGF/CCF; ASBG/NSBG/TSBG - VOIPPM schema
Ceilometer - xxx_DCAECOMMON_VIEWS schema
We load raw data from flat files
PM Alerts (DNR via PACE->UEB->vETL and TCA via vPEC->UEB->vETL)
TCALARMS schema
Fault Traps (Direct into Vertica from DCAE for DCAE process)
xxx_DCAECOMMON_VIEWS schema
Real-time constraints
This interface will be transparent to Vertica
Periodic as they happen
Interface via UEB that interacts directly with Event Listener that inserts records in Vertica
Policy (Direct into Vertica from DCAE for DCAE process)
xxx_DCAECOMMON_VIEWS schema
Real-time constraints
This interface will be transparent to Vertica
Periodic as they happen but not too often
Close Loop (Direct into Vertica from DCAE for DCAE process)
xxx_DCAECOMMON_VIEWS schema
Real-time constraints
This interface will be transparent to Vertica
Expecting about 100 records a day
Inventory (A&AI & INSTAR->CTI->vETL)
xxx_DCAECOMMON_VIEWS schema (A&AI inv)
PMCM schema (INSIGHT inv)
Note: DRI messages to JDB are used to alert vPEC, vPCC and other that files were loaded
CDRs (PCC -> vETL for 15.10 (TA CDR Collectors for 15.07)
BW AS - CDRRAW Schema
ERC ASBG/NSBG - CDRRAW Schema
CDR Alerts (DNR via PACE->UEB->vETL and TCA via vPEC->UEB->vETL)
TCALARMS schema
OUT
vPro (DCAE Analytics Module) – Contact Eric C Noel and Terry Schmalzried
Will come soon – awaiting to move to Vertica from Netezza
Read only access to Vertica views
ECM (Ericson Cloud Manager)
The Closed Loop processing is for Trinity and MCR services. Vertica data is used by call ECM for restarting VMs and other functions. However ECM is going away so we won't be fully doing Closed loop until ECOMP APP-Controller is complete (replacement of ECM). It hasn't started yet
Policy Manager
WBG
PAPT - analyzes CDRs and used for performance analysis. Who owns it? What data is needed for it? Read the CDR data out of Vertica. They process the data, create summaries and then insert summaries in Vertica. How will they get the data?
Other modules that read Vertica from Vertica: TCA and Reporting tools (COGNOS (Steve), MicroStrategy (Nag) and maybe BO).
PURE
PACE
PMMS
INSIGHT

## Remove - Data Model Info (hidden)
Erwin data model check list
1) Confirm/Define missing Domains (in logical mode) in Erwin
2) Remove all old tables/view from IN WORK subject area (NOT FROM THE DM, ONLY FROM THE SUBJECT AREA)
3) After you have executed the XLSm spread sheet against the DM. Follow the check list to do Within Erwin DM:
a. Move all new tables to IN WORK area
b. Define FK from LOAD_FILE_INFO
c. Define PKs in the table
d. Create views
e. Add schemas to tables/views
f. Add partitions as follows change datetime to your column:
i. Raw table : weekly partition clause:
PARTITION BY EXTRACT(year FROM datetime)*100 + EXTRACT(week FROM datetime)
ii. Hourly summary table : Monthly partition clause:
PARTITION BY EXTRACT(year FROM datetime)*100 + EXTRACT(month FROM datetime)
g. Create DDL, check if all the table/views are in the DDL
h. Create a change list
i. Send it to DBAs
Data Model standards
https://tspace.web.att.com/files/app#/file/15200347-002b-4385-9c64-8fcaa7832265