## Sheet1
project_name | pid | pmt | dev_lead | developers | release | sprint_schedule | lpm | pm | scrum_master | se | notes | impact | readiness_status | deployment_cr
VPMS Backend & DB - Wave 2 | 293586 | 464839 | Eric | Patricia (DM, MD, KPI engine) | 1806 | IT1: 12/18/2017 - 1/12/2018 IT2: 1/15/2018 - 2/9/2018 IT3: 2/12/2018 - 3/9/2017 IT4: 3/12/2018 - 4/6/2018 IT5: 4/9/2018 - 5/4/2018 IT6: 5/7/2018 - 6/1/2018 |  | Janet Perrineau | Janet Perrineau | Suryaprakash Mareddy | 1/19: Eric created the tasks in TDP today 1/19: Erica pushed out the entire IT schedule by 1 week. Eric adjusted the dev due date in this file accordingly. 1/17: Surya held a meeting to discuss the 3 single row raw data calculated columns. It was decided to NOT add these columns into the raw tables. AA56 1/16: Surya will discuss the same row calculations with Hui-Tung today and see if VEC/VCC can do it. Will set up a meeting with VETL/Vertica only if VEC/VCC cannot do this. 1/10: Surya held a meeting to determine who should do the same row calculations but it was not resolved. 1/9: Erica Chao is taking over this project from Janet. Iteration schedule was provided. 12/12: In a 2nd story review meeting later today, Janet said that if we have to go into IT 2 then that is fine but try to deliver early in IT2. Eric said that is more realistic for VETL/Vertica. 12/12: Eric attended Surya's story review meeting. Janet provided the IT1 dates of IT 12/18/2017 - 1/12/2018. I told Janet that no development can begin until 2018 due to vacations and that we MIGHT be able to deliver a few days AFTER 1/12/2018. 12/11: Eric decided to assign this project to Patricia instead of Abhishek. Once the developers in Eric's domain run out of bandwidth, then we'll assign projects to Abhishek. 12/11: Eric attended this meeting alone. Found out that Abhishek is located offshore. The VETL/Vertica stories were not reviewed and will be reviewed tomorrow (12/12) 12/11: Eric forwarded story review meeting to Abhishek since he will be assigned to this project. 12/8: Suryaprakash Mareddy scheduled a story review meeting for 12/11 12/5: Janet scheduled the kick off call for 12/6. Eric declined the invite and sent email to Janet to move this meeting to next week after 1712 deployment is over. 11/17: Janet sent email saying this project is ready for story reviews. The reviews will begin on 11/27/2017. 6/1: Eric asked Janet via Q to add him into all related meetings. They are still gathering requirements and no ETA on story review meeting yet. 5/31: Dana informed Eric that this project was assigned to Toni Q but should be assigned to Eric. Eric reassigned it to himself today in iPOR | Code
NexGen SeGW for AIC | 289865 | 457984 | Toni | Rajesh | 1806 |  |  |  |  | Jiya Peng
| 287479CO |  | Eric |  | 1806 1710 | [5 empty] | 3/15: Tony assigned this project to Eric in his iPOR spreadsheet. | On Hold
ADIG on vPE FFA and OSS/BSS development Release 1a | 295793 | 471729/463205 | Huei | Huei/Zhenyuan | 1806 |  |  |  | Lon Tanner | Paul Madarasz |  | code
T07 72c PSD TechOps ECOMP Theme 7 Package 1 - 296151a | 301267 301367 | 470524 or 471913 | Eric | Kshama (DM, MD) | 1806 | DEV: IT49: R10.3 2/12/2018 – 3/12/2018 IT50: R11.1 3/12/2018 – 4/9/2018 IT51: R11.2 4/9/2018 – 5/7/2018 IST: ITR 49: 3/26 Mon – 4/06 Fri (2 wks) ITR 49: 50: 4/09 Mon – 5/04 Fri (4 wks) ITR 49: 50,51: 5/07 Mon – 6/08 Fri (5 wks) |  |  |  | Shau-ann Chang (sc790u) | 1/29: Shau-Ann held a meeting to review the overall project 1/24: Shau-Ann Chang (sc790u) sent a story review invite that will take place on 1/29/2018. | Code | All DMs have been materialized and project is ready to deploy.
VPMS Backend & DB - Wave 2 | 293586 |  | Eric | Patricia (DM, MD, KPI engine) | 1806 | IT49 2/5/2018 - 3/2/2018 IT50 3/5/2018 - 3/30/2018 IT51 4/2/2018 - 4/27/207 |  |  | Erica Chao (ec698j) | Suryaprakash Mareddy (sm8290) | 12/12: In a 2nd story review meeting later today, Janet said that if we have to go into IT 2 then that is fine but try to deliver early in IT2. Eric said that is more realistic for VETL/Vertica. 12/12: Eric attended Surya's story review meeting. Janet provided the IT1 dates of IT 12/18/2017 - 1/12/2018. I told Janet that no development can begin until 2018 due to vacations and that we MIGHT be able to deliver a few days AFTER 1/12/2018. 12/11: Eric decided to assign this project to Patricia instead of Abhishek. Once the developers in Eric's domain run out of bandwidth, then we'll assign projects to Abhishek. 12/11: Eric attended this meeting alone. Found out that Abhishek is located offshore. The VETL/Vertica stories were not reviewed and will be reviewed tomorrow (12/12) 12/11: Eric forwarded story review meeting to Abhishek since he will be assigned to this project. 12/8: Suryaprakash Mareddy scheduled a story review meeting for 12/11 12/5: Janet scheduled the kick off call for 12/6. Eric declined the invite and sent email to Janet to move this meeting to next week after 1712 deployment is over. 11/17: Janet sent email saying this project is ready for story reviews. The reviews will begin on 11/27/2017. 6/1: Eric asked Janet via Q to add him into all related meetings. They are still gathering requirements and no ETA on story review meeting yet. 5/31: Dana informed Eric that this project was assigned to Toni Q but should be assigned to Eric. Eric reassigned it to himself today in iPOR | Code
Automation - End-to-End Incident Management - Release 1 - PI 3 | 298822B | 469049 | Eric | Patricia (DMaaP, EE) | 1802 |  |  | Theresa Siordia-Rybarski (ts1916) | Theresa Siordia-Rybarski (ts1916) | Rick Quagliata (rq2591) | 1/12: Patricia agreed to complete this work by 1/23 and do ST HO on 1/24. Rick provided all the needed info in the story for Patricia. 1/12: Eric will need to locate a developer that can complete development b y 1/23 and do ST HO on 1/24. 1/12: Rick will update this story and create a new story for the audit publishing work 1/11: Rick Quagliata (rq2591) asked if we can do the below Rick(11:52:20 AM): Hi Eric. P&CM_ENT has a project 298822b 1802 which needs a daily audit file published to data router. it will be a simple file which will contain a total for the number of alerts PACE published during the 24 hour period. The subscribing application will be sending me info on the format of this audit file soon. Sufen from PACE thought it would be better for vETL to create this file, instead of PACE. Are you on board with that? Eric Gonzalez (eg7567)(12:06:06 PM): Hi Rick. That sounds good to me. Let me confirm with another person on my team. Hold on Rick(12:09:28 PM): ok Eric Gonzalez (eg7567)(12:44:54 PM): Yes, we can do that Rick(12:45:09 PM): ok great Eric Gonzalez (eg7567)(12:45:23 PM): I see your email so I'll forward it to my team Rick(12:45:55 PM): ok. i am writing the US now. Eric Gonzalez (eg7567)(1:03:00 PM): What release is that PID for? Eric Gonzalez (eg7567)(1:03:08 PM): I cannot check right now due to being in a meeting Eric Gonzalez (eg7567)(1:05:45 PM): Oh wait... Your Q above shows 1802 Rick(1:06:30 PM): yes 1802 PID 298822b Eric Gonzalez (eg7567)(1:07:30 PM): Well, as long as we are given plenty of time to do the work. We'll discuss dates after we review your story Rick(1:07:49 PM): sure. thanks | Code | Project is ready to deploy.
Support Firstnet’s high visibility | QH-MS-1804001 | vetl 471531/vertica 476634 | Toni | Developers: Patricia, Kshama | 1806 |  |  | ? | ? | Justine Lau (jl905g) | 1/23: Eric provided a pure development estimate of 3 pwks to Justine via Q. Mentioned that the estimate will need to be multiplied by 2.5 or 3 to account for scrum calls, questions, ST HO, etc. 1/11: Justine Lau held a QH review meeting today. | Code
Adding GMIS vPE to iTAS | 295793 | 463205 | Huei | Huei/Zhenyuan | 1806 |  |  |  | Lon Tanner | Paul Madarasz |  | code
open DCAE to support Next Gen Virtual Route Reflector (vRR) | 282055d | 471533/469760 | Huei | Huei/Zhenyuan | 1806 |  |  |  | Jane Chung | Jeff Yu |  | Code
T17.13.1 DCAE Platform Evolution | 301368 | 472632/470527 | Huei | Huei/Zhenyuan | 1806 |  | Charles Cook |  | Swati Chauhan | Wen Shang |  | Code
SAREA Automation Optimization and Contended ETH | 294728c | 472635/470103 | Huei | Huei/Zhenyuan | 1806 |  |  |  | Adam Beaver | Jeff Jaggernauth (jj8161) |  | Code
Robocalling TN Authentication (STIR/SHAKEN) - USP | 297122 | 471550/466778 | Huei | Zhenyuan | 1806 |  |  |  | Kris Hubble (wh4355) | Mingming Yu (my2263) |  | Code
| 297131A | 471516 | Eric | Kshama Punj | 1806 | R12.1 2018-07-01 M 4w [6/4/2018 – 7/2/2018] (Note: 18.06 release weekend is 6/09 - 6/10/18) R11.3 2018-06-03 M 4w [5/7/2018 – 6/4/2018] R11.2 2018-05-06 M 4w [4/9/2018 – 5/7/2018] R11.1 2018-04-08 M 4w [3/12/2018 – 4/9/2018] R10.3 2018-03-11 M 4w [2/12/2018 – 3/12/2018] R10.2 2018-02-11 M 4w [1/15/2018 – 2/12/2018] (Note: 18.02 release weekend is 2/10 – 2/11/18) |  |  | Jane Chung (jc1858) | Mingming Yu (my2263) | 2/28: Kshama & Eric attended Jane Chung's grooming meeting. 2/8: Eric & Srinivas attended Mingming's story review meeting 1/25: Mingming Yu (my2263) will have a story review meeting in the near future to discuss the creating and loading of the AAI SRIOV-PF table | Code
| 297519 | 471801 | Eric | Patricia Kshama Srinivas | 1806 | IT50 (R11.1 2018-04-08 M 4w)  3/12/18 – 4/8/18 IT51 (R11.2 2018-05-06 M 4w)  4/9/18 – 5/6/18 |  |  | Kris Hubble (wh4355) | Deepa Saxena (ds521a) Ed Berberich (eb1847) | 3/13: Srinivas and Eric attended Deepa's 2nd story review meeting 3/12: Srinivas and Eric attended Deepa's story review meeting | Code
NoD - Move to AIC3 0&nbsp; Features&nbsp;&nbsp; testing | 291247D | 471545 | Eric | Kshama | 1806 | IT 11.1 3/23/2018 - 4/8/2018 IT 11.2 4/9/2018 - 4/20/2018 |  |  | Lon Tanner | Stephen Lam | 3/23: Srinivas & Eric attended Lon's grooming meeting. Eric pushed the dev due dates to the latest possible date which is 4/20/2018 and Kshama can do DIT earlier if possible. | Code
vUSP Geo-Redundancy Redesign (2+2) | 295390 | 471607/464532 | Huei |  | 1806 | [6 empty] | TSO
New Day vPE Service Assurance and Delivery ADI - 297100a | 297100a | 471713 | Huei | Huei | 1806 | [6 empty] | Code
Robocalling TN Authentication (STIR/SHAKEN) - USP (ID: 297122) | 297122 | 471550/466778 | Huei | Kshama | 1806 | [6 empty] | Code